STATE OF OKLAHOMA

DEPARTMENT OF HUMAN SERVICES

AGING SERVICES

SFY 2015-2018

SFY2018 Update

AREA PLAN ON AGING APPLICATION

FOR

#__9__ Planning and Service Area

| Counties Served: | Caddo, Comanche, Cotton, Grady, |
| --- | --- |
|  | Jefferson, McClain, Stephens and Tillman |

UNDER

THE OLDER AMERICANS ACT

Applicant Agency

|  | The Association of South Central Oklahoma Governments |
| --- | --- |
| Address | 802 West Main**P.O. Box 1647 |
| City/Zip | Duncan, Oklahoma 73534-1647 |
| Telephone | 580.252.0595**800.658.1466 |

Table of Contents

PART A.  OVERVIEW OF NATIONAL AGING NETWORK	4

EXHIBIT 1. DECLARATION OF OBJECTIVES FOR OLDER AMERICANS	4

EXHIBIT 2. REAUTHORIZATION OF THE OLDER AMERICANS ACT	6

EXHIBIT 3. NATIONAL AGING SERVICE NETWORK	8

EXHIBIT 4.  ACL ORGANIZATIONAL CHART (Text Version)	9

PART B.  INTRODUCTION AND OVERVIEW OF PLANNING AND SERVICE AREA	11

EXHIBIT 5.  AREA AGENCY ON AGING MISSION STATEMENT	11

EXHIBIT 6. PROCESS AND PLANNING FOR DEVELOPING THE AREA PLAN	12

PART C.  CONTEXT	13

EXHIBIT 7. ORGANIZATIONAL STRUCTURE	13

EXHIBIT 8. DEMOGRAPHICS IN PLANNING AND SERVICE AREA	15

PART D.  EVALUATIONS, NEEDS, GOALS, OBJECTIVES	19

STRATEGIES AND OUTCOMES	19

EXHIBIT 9. EVALUATION OF CURRENT SERVICES	19

EXHIBIT 10. IDENTIFIED PRIORITY NEEDS	26

EXHIBIT 11. MANAGEMENT PLAN FORM FOR AAA GOALS AND OBJECTIVES	28

EXHIBIT 12. STRATEGIES FOR OUTCOMES	39

PART E.  FEDERALLY REQUIRED FOCUS AREAS	43

EXHIBIT 13. OUTREACH NARRATIVE FOR TARGET POPULATIONS	43

EXHIBIT 14. VOLUNTEER PROGRAM NARRATIVE	48

EXHIBIT 15. SERVICE DELIVERY NARRATIVE	51

EXHIBIT 16. DISASTER PLAN/IMMUNIZATIONS	59

EXHIBIT 17. COORDINATION ACTIVITIES BETWEEN TITLE III AND TITLE VI	60

EXHIBIT 18. LONG RANGE PLAN	61

EXHIBIT 19. COMMERCIAL OR CONTRACTUAL ACTIVITIES	62

PART F.  FINANCIAL MANAGEMENT PLAN	65

EXHIBIT 20. AREA PLAN BUDGET JUSTIFICATION	65

EXHIBIT 21. OMBUDSMAN BUDGET JUSTIFICATION	66

EXHIBIT 22. SUMMARY OF PROCESS USED TO AWARD FUNDS	67

EXHIBIT 23. NEGOTIATED AGREEMENT FOR INDIRECT COSTS	68

EXHIBIT 24. INDIRECT COST RATE PROPOSAL	69

EXHIBIT 25. OKDHS JOB FAMILY DESCRIPTORS FOR OMBUDSMAN	70

PART G.  AREA PLAN APPENDICES	79

# PART A.  OVERVIEW OF NATIONAL AGING NETWORK

## EXHIBIT 1. DECLARATION OF OBJECTIVES FOR OLDER AMERICANS

Section 101.

The Congress hereby finds and declares that, in keeping with the traditional American concept of the inherent dignity of the individual in our democratic society, the older people of our Nation are entitled to, and it is the joint and several duty and responsibility of the governments of the United States, of the several States and their political subdivisions, and of Indian tribes to assist our older people to secure equal opportunity to the full and free enjoyment of the following objectives

(1) An adequate income in retirement in accordance with the American standard of living.

(2) The best possible physical and mental health which science can make available and without regard to economic status.

(3) Obtaining and maintaining suitable housing, independently selected, designed and located with reference to special needs and available at costs which older citizens can afford.

(4) Full restorative services for those who require institutional care, and a comprehensive array of community-based, long-term care services adequate to appropriately sustain older people in their communities and in their homes, including support to family members and other persons providing voluntary care to older individuals needing long-term care services.

(5) Opportunity for employment with no discriminatory personnel practices because of age.

(6) Retirement in health, honor, dignity—after years of contribution to the economy.

(7) Participating in and contributing to meaningful activity within the widest range of civic, cultural, educational and training and recreational opportunities.

(8) Efficient community services, including access to low cost transportation, which provide a choice in supported living arrangements and social assistance in a coordinated manner and which are readily available when needed, with emphasis on maintaining a continuum of care for vulnerable older individuals.

(9) Immediate benefit from proven research knowledge which can sustain and improve health and happiness.

(10) Freedom, independence, and the free exercise of individual initiative in planning and managing their own lives, full participation in the planning and operation of community based services and programs provided for their benefit, and protection against abuse, neglect, and exploitation.

(42 U.S.C. 3001)

## EXHIBIT 2. REAUTHORIZATION OF THE OLDER AMERICANS ACT

As Amended In 2006 (Public Law 109-365) Older Americans

The Older Americans Act Amendments of 2006 integrated the principal elements of AoA’s modernization agenda into the core of the Act. The Act now authorizes all levels of the Network to actively promote the development of consumer-centered systems of long-term care and emphasizes the use of a three-pronged strategy for advancing systemic changes at the state and community level. This strategy includes: empowering individuals to make informed decisions about their care options through Aging and Disability Resource Centers; enabling older people to live healthier lives through the use of evidence-based disease and disability prevention programs, and providing more choices to individuals, especially those at high-risk of nursing home placement and spend down to Medicaid, through the use of flexible service models, including consumer directed care options. (Strategic Action Plan 2008-2012)  Medicaid

Title I:      Declaration of Objectives; Definitions

Title II:    Administration on Aging

Title III:   Grants for State and Community Programs on Aging

-    Part A  -  General Provisions

-    Part B  -  Supportive Services and Senior Centers

-    Part C  -  Nutrition Services

Subpart  1  -  Congregate Nutrition Services

Subpart  2  -  Home Delivered Nutrition Services

-    Part D  -  Disease Prevention and Health Promotion Services

-    Part E  -  National Family Caregiver Support Program

Title IV:    Training, Research, and Discretionary Projects and Programs

-    Part A  -  Grant Programs

-    Part B  -  General Provisions

Title V:     Community Service Employment Program for Older Americans

Title VI:    Grants for Native Americans

-   Part A  -  Indian Program

-   Part B  -  Native Hawaiian Program

-   Part C  -  Native American Caregiver Support Program

Title VII:   Vulnerable Elder Rights Protection Activities

--- Subtitle  A  -  State Provisions

--    Chapter  1  -  General State Provisions

--    Chapter  2  -  Ombudsman Programs

--    Chapter  3  -  Prevention of Elder Abuse, Neglect, and Exploitation:

--    Chapter  4  -  State Legal Assistance Development Program

--- Subtitle  B   -  Native American Organization Provisions

--- Subtitle  C   -  General Provisions

## EXHIBIT 3. NATIONAL AGING SERVICE NETWORK

Working in close partnership with its sister agencies in the U.S. Department of Health and Human Services, Administration for Community Living (ACL) is the official Federal agency dedicated to policy development, planning and the delivery of supportive home and community-based services to older adults, people with disabilities, and their families and caregivers. The ACL works through the national aging network of 56 State Units on Aging, 629 Area Agencies on Aging, 236 Tribal and Native organizations representing 300 American Indian and Alaska Native Tribal organizations, and two organizations serving Native Hawaiians, plus thousands of service providers, adult care centers, caregivers, and volunteers.

## EXHIBIT 4.  ACL ORGANIZATIONAL CHART (Text Version)

The U.S. Administration for Community Living (ACL) is led by the Administrator, who also serves as the Assistant Secretary for Aging. The Administrator is directly supported by the Principal Deputy Administrator. The following staff offices report directly to the Administrator:

- Office of External Affairs

- Office of Regional Operations, which includes ten offices located in various regions of the United States

ACL is comprised of the following units, which report directly to the Administrator:

- Administration on Aging

- Administration on Intellectual and developmental Disabilities

- Center for Disability and Aging Policy

- Center for Management and Budget

The Administration on Aging is led by the Assistant Secretary for Aging, who is directly supported by the Deputy Assistant Secretary for Aging. Reporting directly to the Deputy Assistant Secretary for Aging are the following offices:

- Office of Supportive and Caregiver Services

- Office of Nutrition and Health Promotion Programs

- Office of Elder Rights Protection

- Office of American Indian, Alaskan Native and Native Hawaiian Programs

- Office of Long-Term Care Ombudsman Programs

Reporting directly to the Commissioner on Intellectual and Developmental Disabilities of the Administration on Intellectual and developmental Disabilities are the following offices:

- Office of Program Support

- Office of Innovation

- Office for the President’s Committee for People with Intellectual Disabilities

Reporting directly to the Deputy Administrator of the Center for Disability and Aging Policy are the following offices:

- Office of Policy Analysis and development

- Office of Performance and Evaluation

- Office of Integrated Programs

Reporting directly to the Deputy Administrator of the Center for Management and Budget are the following offices:

- Office of Budget and Finance

- Office of Administration and Personnel

- Office of Grants Management

- Office of Information Resources Management (Taken from ACL website www.acl.gov).

# PART B.  INTRODUCTION AND OVERVIEW OF PLANNING AND SERVICE AREA

## EXHIBIT 5.  AREA AGENCY ON AGING MISSION STATEMENT

ASCOG Supportive Services Division and Area Agency on Aging:  Our mission is to promote independence, quality of life and community involvement through advocacy, support and education.

## EXHIBIT 6. PROCESS AND PLANNING FOR DEVELOPING THE AREA PLAN

ASCOG uses surveys, site visits, public forums, advisory council input, project consultations and public hearings to identify priority needs for the area plan.  Surveys are required for all Title III services in the ASCOG area.  ASCOG Information and Assistance (I&A) service surveys are mailed to participants throughout the year.  Surveys for other services are coordinated annually by the Title III service providers.  The AAA also sends out needs surveys to obtain public input on the needs and priority of services in the planning and services area.

The ASCOG AAA Director and I&A conduct site visits and presentations throughout the year.  During each site visit the AAA Director informally interview seniors eating at nutrition sites and independent senior centers.  The AAA Director also prepares presentations to inform the public about Title III services and to obtain feedback from participants.

Public forums/hearings are scheduled every year in preparation for the four-year area plan and annual updates.  Press releases are mailed to public media to encourage attendance and participation.  During the public forums/hearings the AAA Director will ask for public feedback regarding existing Title III services as well as inquire about unmet needs.  At least one public forum/hearing is scheduled for each county.

Every quarter the ASCOG AAA Advisory Council discusses the current services provided by the AAA.  During each meeting the AAA Director seeks input from the council regarding the area plan goals and progress.

Every quarter the AAA Director informally meets with each project to receive input from and consultation regarding successful Title III services as well as unmet needs.  These meetings are held following the AAA Advisory Council meetings.

Additionally, input is obtained from the I&A regarding unmet needs.  And a needs assessment is sent out to all site managers and project directors to receive input on unmet needs.

Consumer satisfaction surveys are obtained for each service from all projects.  In July 2015 ASCOG requested all projects to start documenting the number of surveys mailed out in addition to a summary of all surveys received.  This should provide additional information in the SFY18 area plan.

# PART C.  CONTEXT

## EXHIBIT 7. ORGANIZATIONAL STRUCTURE

Founded in 1969, the Association of South Central Oklahoma Governments serves Caddo, Comanche, Cotton, Grady, Jefferson, McClain, Stephens and Tillman counties.  Seventy-two communities are members of ASCOG as well as eight counties and ten conservation districts.  In 1990, ASCOG was organized as a public trust.  ASCOG is one of eleven councils of governments (COGs) in Oklahoma.  There are over 400 COGs nationwide.

ASCOG’s overall mission is to improve the efficiency of local government.  ASCOG administers programs under control of local elected officials.  Public policy issues that go beyond a single political boundary are addressed.  Technical, planning, geographical information, management and other professional services are provided to member governments.

ASCOG’s board is made up of 39 trustees including eight mayoral representatives, eight county commissioners, eight conservation district directors, eight at-large representatives, four minority representatives, two Indian tribal group representatives (WCD & KCA) and the Mayor of Lawton.  Officers are elected annually in June and can serve no more than two consecutive terms. Full board meetings are held quarterly at 6:30 p.m. on the third Thursdays of March, June, September and December.  The executive committee is comprised of the above officers, a trustee from each of the counties not represented by an officer, and a minority trustee or Indian Tribal representative.  No county will be represented twice. Meetings are held in January, February, April, May, July, October and November.  There is no meeting in August.  Trustees are reimbursed for mileage.

ASCOG’s staff includes the Executive Director (Ronnie Ward), Directors of Administration, Community and Economic Development, Supportive Services (AAA), Public Safety, Environmental Services and Resource Management.

The Supportive Services Division includes 17 staff involved in aging services, planning, nutrition and other project monitoring, Ombudsman supervisors, managed care (ADvantage), Medicare, Information and Assistance and advocacy.

Membership dues from member governments are used to match state and federal dollars for EDA and aging grant program services.

ASCOG provides certain attributes, including credibility, knowledge, professional integrity, responsiveness, trust, continuity (institutional

memory), information sources, constant relationship amid program changes, liaison to federal, local and state governments, and are there every day for our legislators and elected officials.

## EXHIBIT 8. DEMOGRAPHICS IN PLANNING AND SERVICE AREA

Currently, approximately 64,475 persons aged 60 and older live in the ASCOG AAA Planning and Services Area.

- Of those, approximately 28,695 are female, 27,030 are male,

- 2,387 are African American, 2,260 are American Indian, 682 are Asian, and 1,289 are Hispanic/Latino.

- Approximately 4,926 live in poverty, 1,133 are minorities with low-income, and 512 have limited English speaking proficiency.

- It is estimated that 37,020 live in rural/isolated areas,

- 1,050 are grandparents raising their grandchildren,

- 12,925 live alone

- and 14,747 are veterans.

Population changes in the district reflect the poorest counties have fewer residents in the 2010 Census than in the 2000 Census while the more urban counties and those around the Oklahoma City area have shown significant growth.

ASCOG’s southern three counties of Tillman, Cotton and Jefferson comprise the most rural and poor counties in the area.  These counties are isolated in that the nearest services are located in adjacent counties or even out of state.

The largest accumulation of minorities is in the Lawton/Ft. Sill area in Comanche County, while pockets of persons with limited English speaking proficiency are in Stephens and Tillman counties.

The largest accumulation of older Native Americans exists in Caddo County (Anadarko, Apache and Ft. Cobb).

The largest population of older persons living alone are in Comanche County (Lawton).

The largest population of veterans is also in Comanche County (Lawton/Ft. Sill and Indiahoma).

In State Fiscal Year 2015, ASCOG AAA served approximately 408 seniors with severe disabilities, 75 veterans and 624 at risk for institutional placement with Title III services.

Currently, approximately 5,835 persons aged 60 and older live in Caddo County.

- Of those, approximately 3,185 are female and 2,650 male

- 165 are African American, 1,020 are American Indian, 10 are Asian, and 199 are Hispanic

- 835 are below the poverty line, 349 are low-income minority and 29 have limited English proficiency

- 5835live in rural areas or are isolated

- 105 are grandparents raising grandchildren

- 1,485 live alone, and

- An estimated 1,590 are veterans

Currently, approximately  16,955 persons aged 60 and older live in Comanche County.

- Of those, approximately 9,385 are female and 7,570 male

- 2,275 are African American, 990 are American Indian, 625 are Asian, and 645 are Hispanic

- 1,340 are below the poverty line, 499 are low-income minority and 370 have limited English proficiency

- 2,119 live in rural areas or are isolated

- 430 are grandparents raising grandchildren

- 4,750 live alone, and

- An estimated 5,505 are veterans

Currently, approximately 1,335 persons aged 60 and older live in Cotton County.

- Of those, approximately 745 are female and 590 male

- 39 are African American, 94 are American Indian, 8 are Asian, and 54 are Hispanic

- 115 are below the poverty line, 88 are low-income minority and 15 have limited English proficiency

- 1,748 live in rural areas

- 20 are grandparents raising grandchildren

- 305 live alone, and

- An estimated 314 are veterans

Currently, approximately 9,900 persons aged 60 and older live in Grady County.

- Of those, approximately 5,195 are female and 4,705 male

- 210 are African American, 325 are American Indian, 22 are Asian, and 145 are Hispanic

- 945 are below the poverty line, 71 are low-income minority and 50 have limited English proficiency

- 2,341 live in rural areas

- 255 are grandparents raising grandchildren

- 2,345 live alone, and

- An estimated 2,580 are veterans

Currently, approximately 1,560 persons aged 60 and older live in Jefferson County.

- Of those, approximately 810 are female and 750 male

- 4 are African American, 119 are American Indian, 0 are Asian, and 68 are Hispanic

- 195 are below the poverty line, 22 are low-income minority and 22 have limited English proficiency

- 435 live in rural areas

- 15 are grandparents raising grandchildren

- 400 live alone, and

- An estimated 315 are veterans

Currently, approximately 6,420 persons aged 60 and older live in McClain County.

- Of those, approximately 3,485 are female and 2,935 male

- 45 are African American, 205 are American Indian, 0 are Asian, and 75 are Hispanic

- 545 are below the poverty line, 16 are low-income minority and 0 have limited English proficiency

- 802 live in rural areas

- 145 are grandparents raising grandchildren

- 1,400 live alone, and

- An estimated 1,575 are veterans

Currently, approximately 10,085 persons aged 60 and older live in Stephens County.

- Of those, approximately 5,510 are female and 4,575 male

- 170 are African American, 249 are American Indian, 50 are Asian, and 180 are Hispanic

- 890 are below the poverty line, 62 are low-income minority and 85 have limited English proficiency

- 12,894 live in rural areas

- 155 are grandparents raising grandchildren

- 2,360 live alone, and

- An estimated 2,655 are veterans

Currently, approximately 1,895 persons aged 60 and older live in Tillman County.

- Of those, approximately 1,070 are female and 825 male

- 130 are African American, 18 are American Indian, 0 are Asian, and 205 are Hispanic

- 225 are below the poverty line, 129 are low-income minority and 69 have limited English proficiency

- 536 live in rural areas

- 30 are grandparents raising grandchildren

- 565 live alone, and

- An estimated 469 are veterans

# PART D.  EVALUATIONS, NEEDS, GOALS, OBJECTIVES

# STRATEGIES AND OUTCOMES

## EXHIBIT 9. EVALUATION OF CURRENT SERVICES

In SFY16 ASCOG AAA contracted with the Delta Nutrition Project, MaddieLuke supportive services project, the Center for Creative Living, the Tipton, Grandfield, Minco and Tuttle Senior Centers, the Temple Nutrition Project, the Cyril Nutrition Project and Legal Aid Services of Oklahoma.  Delta served congregate meals in 25 nutrition sites as well as provided transportation services and home-delivered meals to  seven counties.  The Temple Nutrition Project provided congregate and home delivered meals and transportation to the sites in Temple and Walter. The Cyril Nutrition Project provided congregate and home delivered meals and transportation to the Cyril Nutrition Site. MaddieLuke provides provided outreach, coordination of services, health promotion, chore and caregiver services to all eight counties.  Legal Aid provides legal advice and/or representation and legal education in all eight counties.  The Center for Creative Living provided Education and Training to the Lawton and surrounding area.  The senior centers in Grandfield, Tipton, Minco and Tuttle provided coordination of services to their respective senior centers.

ASCOG has contracted with Delta Nutrition for almost 40 years, Legal Aid for over 10 years and MaddieLuke for the last three years.  ASCOG previously contracted with the Center for Creative Living, Minco, Tipton, Grandfield and Tuttle thought SFY16 was their first consecutive year for contracts since SFY14. All three continue to be contractors in SFY17 except Minco and Tuttle.

Title III Services and Surveys for  SFY16:

- Congregate Meals –  489 surveys completed

- Home-Delivered Meals – 259 surveys completed

- Transportation –  52 survey completed

- Outreach –  763 Outreach surveys were offered to participants. 273 surveys completed

- Coordination of Services –  9 surveys completed

- Health Promotion 20 Health promotion surveys were offered to participants. 12 were completed.

- Caregiver Services – 213 Caregiver surveys were offered to participants.  94 were completed. Of the 94, 70 completed Caregiver general services surveys and 72 completed Caregiver Respite surveys.

- Legal Advice –21 completed

- Legal Education –99 completed

- Chore 20 Chore surveys were mailed to participants.  None were returned.

- Education and Training –59 surveys completed

- Information and Assistance –68 surveys completed

STRATEGIES AND OUTCOMES

EXHIBIT 9: EVALUATION OF CURRENT SERVICES

Home Delivered Meals Survey Summary for SFY16:

Of the 259 surveyed, 178 were female, 79 received meals between one and three years and 57 have received meals more than five years. 237 received five meals per week. 224 reported their meals were never left outside. 169 reported they always received meals at the door.  125 reported the meals are never brought inside for them.  112 always eat breakfast.  217 always eat lunch. 132 always eat dinner. 92 always eat snacks.  144 report they are always satisfied with the way the food tastes.  136 report they are always satisfied with the variety of food.  193 reported they are satisfied with the food temperature.  240 are always satisfied with the way the staff treats them.  129 always eat right away.  194 report the meals always arrive when expected.  209 report they eat healthier foods.  172 report improved health.  175 report they feel better.  199 report the meals help them stay at home.  161 report knowledge of the donation system.  237 recommend the service for a friend. 244 report the program has helped them. 133 rated the overall program as excellent with 110 rating the overall program as good.  193 gave no recommendations for improvement.

Congregate Meals Survey Summary for SFY16:

Of the 489 respondents, 267 were female. 202 were aged 60-74 and 177 were aged 75-84.  208 have been on the program for at least five years. 326 report eating five days per week at the site. 472 report comprehension of the donation system. 430 report no problem in getting to the site. 210 report always eating breakfast, 410 report always eating lunch and 296 report always eating dinner.  188 report always eating a snack.  316 are always satisfied with the taste of the meals.  378 are always satisfied with the temperature. 471 are always satisfied with the way the staff treats them. 468 report always feeling welcome. 422 eat healthier because of this program. 393 have shown improved health as a result of this program. 452 report seeing their friends more often. 394 report being able to stay at home because of this program.  468 recommend this program for other seniors. 439 report they were helped by this program. 274 give the overall program an excellent rating and 204 rate the program as good.  No recommendations were received.

STRATEGIES AND OUTCOMES

EXHIBIT 9. EVALUATION OF CURRENT SERVICES

Transportation Consumer Satisfaction Survey Summary for SFY16

Cyril received only one response to the transportation survey in SFY16.  The person reported very positive response on driver timeliness, politeness, ease of use, comfort, arrival time, and scheduling. The purpose of the trips is to attend the nutrition site.

Delta Nutrition received 50 completed survey responses for transportation in SFY16.  The responses showed 36 were completed by females, the majority were aged 60-74, have been in the program 1-3 years, use the program three or more times per month, most use the transportation at least 25% of the time or more, 37 have access to some other transportation – mostly from family, 49 said drivers are always on time, all said drivers are polite, 46 said the vehicles are easy to get in and comfortable, 47 said they always arrive on time, 46 said scheduling is always okay, 41 report getting out of home more, 46 report this helps them live at home, 12 use for medical, 13 for shopping, 46 for nutrition, 1 for business, and six for other purposes, 50 would recommend to a friend, 50 say it helps them.  40 respondents rated the program as excellent.

Outreach Consumer Satisfaction Survey Summary for SFY16

In SFY16, MaddieLuke received 273 responses from Outreach participants.  Of those, 232 strongly agree that they are very satisfied with the way they were treated by MaddieLuke staff.

Health Promotion Consumer Satisfaction Survey Summary for SFY16

12 health promotion surveys were completed in SFY16.  Of those, five rated their health as good, seven said the program helped changed their behaviors a lot, and ten said they would be interested in promoting this workshop to others.

STRATEGIES AND OUTCOMES

EXHIBIT 9. EVALUATION OF CURRENT SERVICES

Caregiver Consumer Satisfaction Survey Summary for SFY16

In SFY16, MaddieLuke received 70 caregiver surveys.  Of those, 67 participants strongly agreed they are very satisfied with services provided by MaddieLuke staff.

Caregiver Respite Consumer Satisfaction Survey Summary for SFY16

In SFY16, MaddieLuke received 72 caregiver respite surveys.  Of those, 29 strongly agreed their quality of life has been improved and 33 strongly agreed this service allowed caregivers to better care for themselves.

Legal Services for Advice and Representation Consumer Satisfaction Survey Summary for SFY16

Out of 21 surveys, 20 rated legal assistance access as very good, 21 rated easy to understand as very good, 21 rated legal assistant knowledge as very good, 12 were between 65 and 74 years of age, 21 rated problem solving as very good, 21 rated paperwork handled very good, 9 said overall was good with 10 making no comment.

Legal Services for Community and Education Consumer Satisfaction Survey Summary for SFY16

Out of 99 community education surveys, 70 rated easy to understand as very good, 73 rated speaker did a good job as very good, 76 rated speaker knowledge as very good, 71 rated learned information as very good, 72 rated amount of time as very good, 56 rated visual aids as very good, 70 rated received information in handouts as very good, 83 did not comment with 12 comments rating as “good.”  The 29 were between ages of 75 and 79

Chore Consumer Satisfaction Survey Summary for SFY16

MaddieLuke mailed 20 surveys to Chore participants.  None were mailed back. One was mailed in August, four in September, six in October, two in November, three in December, one in March, two in April, and one in May.

Coordination of Services Consumer Satisfaction Survey Summary for SFY16

The Consumer Satisfaction Survey results for Coordination of Services were completed by 2 males and 7 females. The majority were aged 71-85. Two were Hispanic and one American Indian. All were rural though five lived in town. Seven heard about the senior center from neighbors.  Seven were very satisfied with the services received. Seven were very satisfied with courtesy of staff.  Six were very satisfied with the taste of the meals. Six were very satisfied with regard to other center programs.

Lawton Education and Training Consumer Satisfaction Survey Summary for SFY16

The Center for Creative Living received 59 completed surveys for SFY16. Of those 45 were from females, 26 were from aged 70-79, 51 from Caucasian participants, 7 report making less than $11,880 while 24 report making more than 28,440, none were grandparents raising grandchildren, 41 have a disability, 58 are still working, 29 volunteer and 43 report being victims of fraud or abuse. 58 report participating at the center at least weekly.  10 would like to travel on center trips. 48 were very satisfaied with service of staff.  49 are very satisfied with the office hours of the center. 45 are very satisfied with the center’s newsletter and handouts.  44 are very satisfied with accessibility of services.  47 are very satisfied with the site atmosphere. 37 are very satisfied with the variety of services.

Information and Assistance Survey Summary for SFY16

68 I&A surveys were returned for SFY16.

I&A was friendly and easy to understand Yes - 59; Somewhat or incomplete – 9; No – 0.

I&A Knew what they were talking about Yes - 58; Somewhat or incomplete - 10; No – 0.

Satisfied with service received… Very satisfied 51; Somewhat or incomplete  17, Not Satisfied – 0.

## EXHIBIT 10. IDENTIFIED PRIORITY NEEDS

The ASCOG AAA needs assessment process includes the following:

- A public hearing

- Holding community forums

- Administration of survey instruments to older consumers, service providers, advocates and other interested persons

- I&A and Outreach identified gaps in services

- An analysis of the results of the needs assessment activities

ASCOG AAA sent a needs assessment survey (see summary of results below) to all Title III nutrition sites in all eight counties as well as to other Title III providers, advocates and other interested persons.  Hundreds of assessments were returned. Our staff scheduled public forums in all eight counties.

According to the needs assessment survey, the following needs were identified (in order of highest need to lowest):

1. Nutrition/Senior Center on-site meals

2. Home Delivered Meals

3. Access to healthcare

4. Help with Utility Bills and

5. Help with dentures (tie)

ASCOG AAA hosted public hearings in each county to obtain feedback into the area plan and comments on needs and services.  Public hearings were hosted in Ringling, Ryan, Frederick, Lawton, Duncan, Walters, Chickasha and Anadarko.

Most centers had little to comment save their desire to keep their congregate meal centers open.  Many questions were asked about possible budget reductions in SFY17 and SFY18.  Lawton North participants had many comments related to their food preferences which were referred to Delta Nutrition for consideration.  One comment was made that nursing home residents who also receive home health are “double-dipping.” Questions were asked about the Senior Community Services Employment Program. Requests were made for utility assistance.

The ASCOG Advisory Council reviewed the draft area plan during their December 13, 2016 meeting.  No further comments were made.

The ASCOG Board of Directors are scheduled to review and comment on the area plan during their February 16 Executive Committee meeting.

The MaddieLuke Outreach service has identified through the outreach assessment tool:

- Transportation

- Utility Assistance

- Health care cost assistance

- Food assistance

- Congregate and Home Delivered meals

The ASCOG I&A, Kristina Brown, has identified the following gaps in services:

- Food insecurity

- Daily Living Expenses (Utilities, Medications, Co-pays, etc.)

- Personal Care Assistance

- Transportation

- And Healthcare

Based on the consistency found between the needs assessment survey and the responses from public forums/hearings as well as the gaps identified by the I&A program, ASCOG AAA has identified the following top five needs to address in SFY18 and following (ranked in order of priority):

1. Nutrition/Senior Center on-site meals

2. Food Assistance

3. Increased Access to transportation

4. Utility Assistance

5. Health Insurance Counseling

Explain in narrative how the identified  needs  will be addressed in SFY18

In SFY18, ASCOG will work to address these top five identified needs.  ASCOG will continue to advocate for resources, hoping to protect senior nutrition as a valuable service.  ASCOG will continue to leverage CENA and county sales tax funding to support nutrition sites who, due to funding reductions, must go independent of Title III funding.  ASCOG will continue to participate in the Senior Farmers Market Nutrition Program and will continue to participate in partnership opportunities with community food banks and the regional food bank. ASCOG will continue funding transportation and will RFP transportation funding to communities where there are gaps in services.  ASCOG has already released Masonic funding to pay for utility assistance effective January 1, 2017.  ASCOG will continue to contract with the Oklahoma Insurance Department, or other managed care insurance providers, to provide health insurance counseling.

## EXHIBIT 11. MANAGEMENT PLAN FORM FOR AAA GOALS AND OBJECTIVES

| GOAL: #1 |  |  |  |  |  |  |  | OBJECTIVE: #1 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enable people with disabilities and older adults to live in the community through the availability of and access to high-quality long-term services and supports, including supports for families and caregivers. |  |  |  |  |  |  |  | Hold public forums no later than March 31, 2015 to discuss transition of available site-based service funding to home-based service funding while mitigating any loss to congregate nutrition sites. |  |  |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |  |
|  |  |  | jul | aug | sept |  | oct |  | nov | dec |  | jan | feb | mar |  | apr | may | jun |  |  |  |
| 1. | Schedule public forums in Lawton, Duncan and Chickasha. Completed: Public forums have been scheduled at the Sites in each county. Public forums and public hearings are Interchangeable. | Jan 31 |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  | AAA Planner |  |
| 2. | Prepare press releases for public forums. Send out press releases no later than ten days prior. Completed: by Planner. | Feb 28 |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  | AAA Planner |  |
| 3. | Facilitate public forum discussion and include public Comment in area plan updates. Completed: by Director for public forums through January 27. | Mar 31 |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  | Director/AAA Planner |  |

EXHIBIT 11. MANAGEMENT PLAN FORM FOR AAA GOALS AND OBJECTIVES for 2015-2018

| GOAL: #1 |  |  |  |  |  |  | OBJECTIVE: #2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enable people with disabilities and older adults to live in the community through the availability of and access to high-quality long-term services and supports, including supports for families and caregivers. |  |  |  |  |  |  | No later than June 30, 2015, coordinate and promote two annual public events and publicity campaigns that address existing in-home services and supports with special focus on home-delivered meals, home repairs, transportation and home health services. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Schedule public events in Lawton and Duncan and Develop committee to support these events in future years. Completed: Lawton event was successfully completed on June 26. Duncan event was conducted for September 24. | Jan 31 |  |  |  |  |  |  |  |  | X |  |  |  |  |  | I&A |
| 2. | Prepare press releases for public events. Send out press releases no later than two weeks prior. Completed for both events. | Apr 30 |  |  |  |  |  |  |  |  |  |  |  | X |  |  | I&A |
| 3. | Facilitate public events and coordinate with event committee. Completed for both events. | June 30 |  |  |  |  |  |  |  |  |  |  |  |  |  | X | Director/I&A |

| GOAL: #1 |  |  |  |  |  |  | OBJECTIVE: #3 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enable people with disabilities and older adults to live in the community through the availability of and access to high-quality long-term services and supports, including supports for families and caregivers. |  |  |  |  |  |  | No later than March 31, 2017, hold public forums to educate the public on potential changes and to receive input regarding said changes to long-term care services and supports in response to the Oklahoma Health Care Authority request for proposals for coordinated care. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Schedule public forums in Lawton, Duncan and Chickasha. In Progress | Feb 15, 2017 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | AAA Director |
| 2. | Prepare press releases for public forums. Send out press releases no later than ten days prior. Completed | Feb 28, 2017 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | AAA I&A |
| 3. | Facilitate public forum discussion and include public Comment in area plan updates. In progress | Mar 31 2017 |  |  |  |  |  |  |  |  |  |  | X |  |  |  | Director |

| GOAL: #2 |  |  |  |  |  |  | OBJECTIVE: #1 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implement management and workforce practices that support the integrity and efficient operations of programs serving people with disabilities and older adults and ensure stewardship of taxpayers’ dollars. |  |  |  |  |  |  | Initiate an annual fiscal management and loss prevention training for existing service providers, no later than May 31, 2015. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Schedule annual training in May in coordination with all Title III providers. Completed: June 18, 2015 | Jan 31 |  |  |  |  |  |  |  |  | X |  |  |  |  |  | Director/Accountant |
| 2. | Recruit trainers for annual training to discuss fiscal Management policy and procedures and best practices. Completed: Trainers included ASCOG AAA staff, Ken Jones from ODMHSAS, Red Cross staff and OSU Ext. Office staff. | Feb 28 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | Director/Accountant |
| 3. | Facilitate training in coordination with providers and their Staff. Completed successfully on June 18. | May 31 |  |  |  |  |  |  |  |  |  |  |  |  | X |  | Director/Accountant |

| GOAL: #2 |  |  |  |  |  |  | OBJECTIVE: #2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implement management and workforce practices that support the integrity and efficient operations of programs serving people with disabilities and older adults and ensure stewardship of taxpayers’ dollars. |  |  |  |  |  |  | No later than April 30, 2015, present policy changes to the ASCOG AAA Advisory Council, requiring MOUs between nutrition projects and independent senior centers where nutrition sites are co-located |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Draft new policy and procedures in coordination with Title III Nutrition Project Completed: No new policy was needed. Added existing Policy to quarterly assessments. | Jan 31 |  |  |  |  |  |  |  |  | X |  |  |  |  |  | AAA Planner |
| 2. | Publish policy draft to Advisory council at least ten days Prior to April AAAAC meeting. Completed. | Mar 31 |  |  |  |  |  |  |  |  |  |  | X |  |  |  | AAA Planner |
| 3. | Make changes as required by AAAAC and obtain AAAAC Approval to new policy in April meeting. Completed: no changes needed in policy. Procedure Changes adopted by collaborative committee made up of AAA Staff and Title III Project Directors. | Apr30 |  |  |  |  |  |  |  |  |  |  |  | X |  |  | Director/AAA Planner |

| GOAL: #2 |  |  |  |  |  |  | OBJECTIVE: #3 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implement management and workforce practices that support the integrity and efficient operations of programs serving people with disabilities and older adults and ensure stewardship of taxpayers’ dollars. |  |  |  |  |  |  | No later than December 31, 2016, present a code of ethics policy for Title III employees and volunteers to the ASCOG AAA Advisory Council, requiring all Title III employees and volunteers to sign a code of ethics prohibiting activities that would damage the integrity of Title III programs and could potentially harm participants of Title III services. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Draft new code of ethics and procedures in coordination with Title III contractors. Completed | Sept. 30, 2016 |  |  | X |  |  |  |  |  |  |  |  |  |  |  | AAA Director |
| 2. | Publish draft or ethics and procedures to Advisory council at least ten days Prior to April AAAAC meeting. Completed | Nov 30 2016 |  |  |  |  |  | X |  |  |  |  |  |  |  |  | AAA Planner/I&A |
| 3. | Make changes as required by AAAAC and obtain AAAAC Approval to new ethics and procedures in December mtg. Completed | Dec 31 2016 |  |  |  |  |  |  | X |  |  |  |  |  |  |  | Director/AAA Planner |

| GOAL: #3 |  |  |  |  |  |  | OBJECTIVE: #1 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Advocate to ensure the interests of people with disabilities, older adults and their families are reflected in the design and implementation of public policies. |  |  |  |  |  |  | No later than June 30, 2015, initiate an annual policy conference for community partners in the ASCOG PSA, that will address service availability, participant safety and fraud prevention, obstacles to accessibility and fiscal management. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Schedule annual conference in coordination with community Partners, stakeholders and policy makers who make up Conference committee. Completed in June Expo. | Jan 31 |  |  |  |  |  |  |  |  | X |  |  |  |  |  | I&A/AAA Planner |
| 2. | Recruit speakers and facilitators for the conference. Completed in June Expo. | Feb 28 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | I&A/AAA Planner |
| 3. | Facilitate policy conference with help of community Partners and committee members. Completed in June Expo. | June 30 |  |  |  |  |  |  |  |  |  |  |  |  |  | X | I&A/AAA Planner/Director |

| GOAL: #3 |  |  |  |  |  |  | OBJECTIVE: #2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Advocate to ensure the interests of people with disabilities, older adults and their families are reflected in the design and implementation of public policies. |  |  |  |  |  |  | No later than April 30, 2015, establish at least five MOUs with community partners who serve older Oklahomans in the ASCOG PSA. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Schedule MOU meetings with community partners. Completed | Jan 31 |  |  |  |  |  |  |  |  | X |  |  |  |  |  | AAA Planner |
| 2. | Establish written MOUs with at least five community Partners, especially with partners who work with not only Persons 60 and older but also disabled persons. Completed. In January 2015, new procedure was Developed to require MOUs be signed by ED of ASCOG. | Feb 28 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | AAA Planner |
| 3. | Complete AAAAC approval and signatures of MOUs no Later than April 30, 2015. Completed. | Apr 30 |  |  |  |  |  |  |  |  |  |  |  | X |  |  | AAA Planner/Director |

| GOAL: #3 |  |  |  |  |  |  | OBJECTIVE: #3 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Advocate to ensure the interests of people with disabilities, older adults and their families are reflected in the design and implementation of public policies. |  |  |  |  |  |  | No later than September 30, 2016, participate and support in the annual Oklahoma Silver Haired Legislature event and annual meeting. |  |  |  |  |  |  |  |  |  |  |
| # | ACTION STEPS | DUE DATE | FIRST QUARTER |  |  | SECOND QUARTER |  |  |  | THIRD QUARTER |  |  |  | FOURTH QUARTER |  |  | STAFF POSITIONS ASSIGNED ACTION STEPS |
|  |  |  | jul | aug | sept | oct |  | nov | dec |  | jan | feb | mar | apr | may | jun |  |
| 1. | Assist OSHL Executive Committee and local ASCOG OSHL group in preparing bills for the annual OSHL. Ongoing | July 31 2016 | X |  |  |  |  |  |  |  |  |  |  |  |  |  | I&A/AAA Director |
| 2. | Assist OSHL in recruiting speakers and facilitators for the Annual OSHL. Ongoing | July 31 2016 | X |  |  |  |  |  |  |  |  |  |  |  |  |  | I&A/AAA Director |
| 3. | Facilitate OSHL annual event in OKC. Ongoing | Sep 30 2016 |  |  | X |  |  |  |  |  |  |  |  |  |  |  | I&A/AAA Director |

## EXHIBIT 12. STRATEGIES FOR OUTCOMES

In  SFY17, ASCOG contracts with three nutrition projects (Delta, Temple and Cyril),  two coordination of services projects (Grandfield,  and Tipton ), one supportive services project (MaddieLuke), one education and training project (Center for Creative Living) and one legal aid project (Legal Aid Services of Oklahoma).

Delta Nutrition Project:

- Reaching target population:  Delta currently provides congregate and home delivered meals and transportation to 20 nutrition sites in seven counties.  Delta serves two urban counties, one with high populations of low-income minorities.  Delta serves six rural counties, each reaching target populations.  Delta has worked with the Alzheimer’s association in Comanche county, the Kiowa/Comanche/Apache tribes, OHAI and MaddieLuke to coordinate outreach,

- Quality of program service delivery: Delta’s food cost per plate is about $1.50, compared to $1.90 at Project Heart and more than $2.00 at Temple and Cyril.  Participants have complained less about food quality in the last year.

- Level of participation and engagement: Delta’s participation at certain sites such as Walters, Cement, and Wayne have held steady while seeing dramatic increases in Cache and Marlow due to changes in management and cooking processes. However, due to decreasing funding in ADvantage meals, Delta serves only 20 sites in SFY17 compared to 25 in SFY16.  Currently Delta is serving approximately 1033 congregate meal participants and 566 home delivered meal participants.  Delta no longer provides the transportation service.

Temple Nutrition Project:

- Reaching target population:  Temple serves a rural county with a small Hispanic population.   Temple has maintained marketing in local newspapers but no longer serves the Walters site.

- Quality of program service delivery:  Temple meal cost is about $2.00 per meal and participant satisfaction is higher since last year.  Participants continue to also have more input into the menu provided.

- Level of participation and engagement:  Temple is currently serving  the same number of participants as the Temple  site served a year ago  Currently Temple is serving 36 congregate participants and 14 home delivered meal participants. Temple no longer provides the transportation service.

Cyril Nutrition Project:

- Reaching target population: Cyril serves a rural population in Caddo County.  Cyril has coordinated services with area tribes and has worked to obtaining an MOU with those tribes. Cyril has also maintained marketing of the program.

- Quality of program service delivery:  Cyril currently provides approximately $2.00 per plate for food cost.  Participant satisfaction has increased since Cyril took over the Cyril Nutrition Site.

- Level of participation and engagement:  In  Currently Cyril has declined in SFY17.  Currently Cyril provides congregate meals to 34 participants, home delivered meals to 24 participants and transportation to 3 participants.

Grandfield Senior Center:

- Reaching target population: Grandfield serves a remote, rural population, including a low-income Hispanic population.

- Quality of program service delivery:  Grandfield provides quality meals, senior activities and health promotion activities through the coordination of services service. Activities include quilting, chair aerobics, painting and other recreational and educational activities.

- Level of participation and engagement:  In SFY17, Grandfield serves about 132 participants.

Tipton Senior Center:

- Reaching target population: Tipton serves a remote, rural portion of Tillman County.

- Quality of program service delivery:  Tipton provides quality services including meals, concerts and dominos, as well as other recreational and educational activities.

- Level of participation and engagement: In SFY17, Tipton is serving approximately 122 participants.

MaddieLuke Supportive Services:

- Reaching target population:  MaddieLuke provides the Outreach service for all eight counties.  They target low-income minorities, rural, isolated and living alone seniors, tribal governments, seniors with severe disabilities and coordinate with the Alzheimer’s Association.

- Quality of program service delivery:  MaddieLuke continues to provide improved outreach services as well as improved caregiver services.  MaddieLuke has had trouble starting support groups due to lack of interest.  MaddieLuke has improved quality of chore services through safer protocols.

- Level of participation and engagement:    So far in SFY17, MaddieLuke has served 55 participants with caregiver access, 14 with caregiver counseling, 27 with caregiver respite, 6 with chore services, 8 with GRRC access, 2 with GRRC counseling, 5 with GRRC respite, and 241 with outreach.  Decreases in participation is a direct result of late notice of grant awards for SFY17.

Center for Creative Living:

- Reaching target population: The Center for Creative Living is located in Lawton, OK, where the highest prevalence of low-income minorities exists in ASCOG’s planning and service area.  However, they are not serving or reaching a proportional number of low income minorities.  CCL has reached out to local tribes in the Lawton area as well as the Alzheimer’s Association, MaddieLuke and OHAI.

- Quality of program service delivery:  CCL provides quality education and training activities.  They have increased the number of classes provided by guest speakers.

- Level of participation and engagement:  The Center for Creative Living has served about 321 participants with education and training.

Legal Aid Services of Oklahoma:

- Reaching target population:  Legal Aid serves six of ASCOG’s eight counties with some provisional services to the other two counties.  Legal Aid uses senior center presentations as its primary outreach tool.

- Quality of program service delivery:  Legal Aid continues to provide quality services in accordance with their consumer satisfaction surveys.

- Level of participation and engagement: In SFY17, Legal Aid’s level of participation is unknown as AIM numbers do not reflect number of persons served due to confidentiality.  Jefferson County continues to be underserved.

# PART E.  FEDERALLY REQUIRED FOCUS AREAS

## EXHIBIT 13. OUTREACH NARRATIVE FOR TARGET POPULATIONS

1.  Document the amount of Title III B (federal) funds expended in SFY16 as required by OAA Section (306)(a)(2):

Access (306)(a)(2)(A): $175,241

  - (A) transportation;   $65,649

  - (B) outreach; $84,708

  - (C) information and assistance;  $24,884

  - (D) assisted transportation; $0

  - (E) case management; $0

  - (F) health services, including mental health services; $0

In-home (306)(a)(2)(B): $12,469

  - (A) homemaker; $0

  - (B) chore;  $12,469

  - (C) personal care; $0

  - (D) home repair;  0

Legal (306)(a)(2)(C): $22,480

  - (A) legal counseling and representation;  $19,037

  - (B) community education on legal matters;   $3,443

  - (C) information and assistance on legal matters; $0

2. Evaluation of Outreach Services for SFY17

MaddieLuke’s main focus is on rural areas, low-income households, and persons with disabilities. MaddieLuke is targeting relationships with community sponsors who specialize in serving individuals with severe disabilities, Alzheimer’s and related diseases, and their caregivers.  These providers include legal aid, the Alzheimer’s association and home health providers. MaddieLuke is also targeting community partners such as local DHS offices, who work with older individuals needing assistance with activities of daily living and instrumental activities of daily living.

MaddieLuke has scheduled canvassing for its outreach workers.  They will target low-income neighborhoods and senior adult housing to ensure those in need are aware of available community services.  This will include canvassing in low-income urban areas such as Lawton.

MaddieLuke will develop referral sources by developing memoranda of understanding with local service providers such as home health agencies, existing Title III services providers, marketing to health professionals and hospital discharge planners and caregiver services providers.  MaddieLuke will focus marketing where referral sources are effective and will then focus canvassing and other outreach methods in areas where referrals are limited.

3. Explain how each target group will be reached in SFY18

In SFY18, ASCOG will continue to focus on outreach per the following:

- Services determined to be the greatest areas of need in the mandated target population in the PSA:

  - (1) residing in rural areas; home repair, home health, home delivered meals, congregate meals, and transportation.

  - (2) with greatest economic need, with particular attention to low income minority individuals; transportation, congregate meals, home delivered meals, home health and chore.

  - (3) with greatest social need, with particular attention to low income minority individuals; transportation, congregate meals, home delivered meals, home repair and home health.

  - (4) with severe disabilities; transportation, home delivered meals, home repairs, home health, congregate meals.

  - (5) with limited English speaking ability; transportation, congregate meals, home delivered meals, home health and home repair.

  - (6) with Alzheimer's disease or related disorders with neurological and organic brain dysfunction and the caretakers of such individuals; transportation, congregate meals, home delivered meals, home repair and home health.

  - (7) living alone; transportation, congregate meals, home delivered meals, home repair and home health.

  - (8) with impairments in activities of daily living (ADLs), instrumental activities of daily living (IADLs), or both. transportation, home delivered meals, home repairs, home health, congregate meals.

- Identify Title III services determined to be the greatest areas of need of the mandated target population of the PSA for SFY16.

o	766 outreach intakes completed in SFY16 Three people were referred to Adult Protective Services, forty others were referred to other non-Title III services such as ADvantage, Medicare Counseling, Prescription Drug assistance and other DHS referrals.

Feedback was requested from ASCOG subcontractors by asking the following questions:

1.  The effectiveness & evaluation of the outreach methods used by you or an outside source. (Are the methods used by your outreach person working? Are target groups being reached? What works, what doesn’t? Suggestions? Be specific please).

2.  Address how each target group in your PSA (planning and service area) is being reached. (How are your target folks being approached? In-person? By mail/email? By phone? Media? Be specific please).

3.  List the Title III services determined to be the greatest areas of need of the mandated target population in the PSA.  (What services do your folks wish were offered? Were better? Were done away with? Be specific please).

We received the following feedback from the Center for Creative Living:

- The methods we use are working very well and we have a high participation rate.  All targeted groups are being reached.  We work this very well so I have no suggestions.

- We reach ours when they come to the CCL.  We ask them in person to complete the surveys and explain the importance of it.  They are more than happy to comply.

- No night time events, they don’t like to drive at night.  Less winter events, won’t drive in bad weather.  And they want more bingo.

We received the following feedback from MaddieLuke:

1. Outreach efforts have proven to be effective. MaddieLuke has a Memorandum of Understanding with Delta Nutrition which states that Delta will refer all participants in need of assessment/Outreach to MaddieLuke. In addition to the Delta partnership, MaddieLuke has a strong social media presence through our company Facebook page. Our marketing efforts include presentations at local hospitals, home health agencies, schools, churches, civic and community organizations. Minorities, rural residents, individuals with dementia/other cognitive impairments, and ESL participants have been targeted through area partners who are focused on the same groups but do not provide the same services. MaddieLuke partners with local libraries and DHS to reach ESL participants. MaddieLuke partners with the Alzheimers Assocation to reach participants diagnosed with dementia. Minorities are targeted through civic and community organizations like Douglass Eastside along with local churches. Rural participants account for all but two of our counties and we receive referrals from multiple partners in all rural counties.

2. Target groups are reached through partner referrals, social media posts, press releases, and phone calls from MaddieLuke.

3. MaddieLuke participants would like a reliable, affordable transportation provider. Food security continues to be a one in four participants issue and more local resources are needed, especially resources that do not use poverty guidelines to determine who receives assistance. Mental health awareness and more mental health resources are needed for caregivers suffering burn out and for participants who are struggling to cope with major changes in circumstances (illness, loss of a spouse, etc…)

Participants continue to advise MaddieLuke that Caregiver and Grandparent Support Groups are of no value to them because they do not want to use the time away from a care recipient/grandchild to sit in a group of people they don’t know when they could be spending the time with their actual support system of family and friends.

5. Identify methods used by outreach project to identify new participants(in SFY18).

- Outreach methods used to identify new participants:

  - (1) residing in rural areas; coordination with other rural agencies, press releases to rural newspapers, advocacy with state policy leaders regarding rural policy, canvassing at low income housing areas, social media and brochures.

  - (2) with greatest economic need, with particular attention to low income minority individuals; public presentations, coordination with other urban agencies, workshops, town hall meetings, news articles addressing stigmas, press releases to local newspapers, canvassing low-income housing areas, and brochures.

  - (3) with greatest social need, with particular attention to low income minority individuals; social media, coordination with home base service agencies, workshops, town hall meetings, news articles addressing stigmas, co-promotion of local events such as Kindred Community, press releases to local newspapers, canvassing low income housing areas and brochures.

  - (4) with severe disabilities; coordination with agencies which serve persons with disabilities, build network of partnership with long-term care providers to address needs of spouses, working with Developmental Disability providers, social media, press releases and brochures.

  - (5) with limited English speaking ability; press releases to foreign language media contacts, social media, outreach to churches working with foreign-language services and populations, and brochures.

  - (6) with Alzheimer's disease or related disorders with neurological and organic brain dysfunction and the caretakers of such individuals; coordination with the Alzheimer’s Associations, partnering with Support Groups providers with Alheimer’s caregivers, press releases, social media to target caregivers, and brochures.

  - (7) living alone; social media, coordination with home base service agencies, press releases to local newspapers, workshops, town hall meetings, news articles addressing stigmas, co-promotion of local events such as Kindred Community, canvassing low income housing areas and brochures.

  - (8) with impairments in activities of daily living (ADLs), instrumental activities of daily living (IADLs), or both; coordination with agencies which serve persons with disabilities, social media, direct mail marketing to provider lists such as the ASCOG provider list as well as any other agencies maintaining lists, press releases and brochures.

- Counties with highest mandated target populations:

  - (1) residing in rural areas; Stephens County.

  - (2) with greatest economic need, with particular attention to low income minority individuals; Comanche County.

  - (3) with greatest social need, with particular attention to low income minority individuals; Cotton County.

  - (4) with severe disabilities; Comanche County.

  - (5) with limited English speaking ability; Comanche County.

  - (6) with Alzheimer's disease or related disorders with neurological and organic brain dysfunction and the caretakers of such individuals; Comanche County.

  - (7) living alone; Comanche County.

  - (8) with impairments in activities of daily living (ADLs), instrumental activities of daily living (IADLs), or both. Comanche County.

## EXHIBIT 14. VOLUNTEER PROGRAM NARRATIVE

ASCOG recruits volunteers to serve on the AAA Advisory Council, Oklahoma Silver-Haired Legislature, and Ombudsman program. Volunteers are also recruited by Title III sub-grantees for serving meals, meal delivery, site coordination, outreach, checking on frail homebound, emergency management and caregiving.

ASCOG’s Advisory Council membership is appointed by members of the ASCOG Board of Trustees.  When trustees are unsure who to appoint, ASCOG AAA staff will recruit members by contacting senior centers and nutrition sites, and through public service announcements and other marketing methods like internet marketing.  OSHL members are automatically members of the ASCOG AAA Advisory Council.  Advisory Council members receive orientation and annual training to explain their duties as members of the advisory council.

ASCOG has one of the most active OSHL groups in the state.  OSHL members are recruited by maintaining bi-annual elections at all CENA senior centers and Title III nutrition sites.  PSAs and internet marketing are also used to recruit OSHL members.  OSHLAA provides bi-annual training to OSHL members.  They also receive training as Advisory Council members.

ASCOG Ombudsman Supervisors send out monthly recruitment PSAs for Ombudsman volunteers.  Currently there are ten Ombudsman volunteers.  One Ombudsman volunteer is also on the AAA Advisory Council.  Ombudsman Supervisors provide regular training for volunteers in accordance with the direction of the State Ombudsman.

Additionally, ASCOG regularly recruits advocates for issues related to aging and disability services.  ASCOG publishes a regular blog called the ASCOG Advocate to help train advocates in the area by keeping them up-to-date on current issues.  Advocates serve on regional or statewide advocacy groups such as the Oklahoma Silver-Haired Legislature, the ASCOG AAA Advisory Council, OSHLAA Executive Committee, the Alliance on Aging, or the State Council on Aging.

In SFY17, ASCOG I&A, Medicare and Ombudsman staff have used press releases, Facebook posts, on-site presentation and website blog posts to recruit new volunteers for Medicare, advocacy and Ombudsman volunteer programs.  Ombudsman Supervisors have increased their volunteers from 5 to 7 so far in SFY17.  So far we have been unable to fully train three seniors who came forward as Medicare volunteers do to training requirements at OID.

Recruitment efforts have been more successful in finding new advisory council and OSHL volunteers.  So far in SFY17 at least three new members of OSHL have been recruited and also serve on the advisory council and in advocacy roles.

Also in SFY17, we have recruited two volunteers to assist at the AAA with filing paperwork and assisting with the Masonic program. Their training for this is expected to begin in January 2017.

In SFY18, we will continue to recruit through on-site presentations and social media posts the need for volunteers and hope to add additional volunteers in the role of Ombudsman and in the role of administrative assistants at the AAA.  The Ombudsman volunteer program is at risk because of continued funding losses and the inability of the AAA to reimburse mileage.  We are working on finding ways to pay volunteer milage to assist with the recruitment of Ombudsman volunteers.

## EXHIBIT 15. SERVICE DELIVERY NARRATIVE

In SFY17, ASCOG contracts with Delta, Temple and Cyril for congregate meals, home delivered meals and transportation services.  ASCOG contracts with MaddieLuke for caregiver/grandparents raising grandchildren access to services, information about services, groups and respite services.  ASCOG contracts with MaddieLuke for outreach, chore and health promotion programs.  Home repair was discontinued for SFY 16 due to a budget reduction.

In SFY17, ASCOG is providing direct service delivery of the following Title III services:  information and assistance, I&A education, ombudsman services, nutrition counseling and nutrition education.

ASCOG is on track to provide 68 units of nutrition counseling,  4,084 units of nutrition education, and 356 units of I&A.  The I&A is also starting to provide presentations and press releases which will increase the number of I&A Education units.

Ombudsman services were provided through two full-time Ombudsman Supervisors and their volunteers.  The Ombudsman Supervisors were responsible for 2,180 nursing home residents in 39 long-term care facilities.

ASCOG  has two Ombudsman Supervisors who also track volunteers.  The Ombudsman program is under the direction of the State Ombudsman.

Legal Aid services saw a decrease in SFY 2015, but within the parameters of reduced funding is on track to provide over 1,000 units of legal aid services.

In  SFY17, ASCOG continues to work with the Delta, Cyril and Temple nutrition projects to increase the quality of service and customer satisfaction. We will continue to work with the supportive services project to continue increasing units of service, as well.

| 1. SERVICE AREA INCLUDES THE FOLLOWING COUNTIES: |  |  |  |
| --- | --- | --- | --- |
| Caddo, Comanche, Cotton, Grady, Jefferson, McClain, Stephens & Tillman |  |  |  |
| II. NAME OF SERVICE: |  |  |  |
| Information and Assistance for SFY2018 |  |  |  |
| III. (A) $ Unit Cost | (B) $ Total Funding | (C) # Units | (D) Unduplicated Persons Served |
| $63.75 | $17,212 | 270 | 200 |
| IV. Formula used to calculate unit cost: |  |  |  |
| $17,212 total funding divided by 270 units of service = $63.75 |  |  |  |
| V. Show the breakdown of Total Funding for Service: |  |  |  |
| 270 units of service multiplied by $63,75 equals $17,212. |  |  |  |
| VI. Activities to Meet the Scope of Work: |  |  |  |
| 1. ASCOG will market the Information and Assistance programs through public presentations, brochures, fliers, email blasts, press releases, blogs and letters to focal points. |  |  |  |
| 2. ASCOG will ensure that an approved 02AG002E Older Americans Act Assessment (modified for I&A) is completed for each eligible participant who contacts or is referred to the Information and Assistance Specialist (I&A). The I&A service is a one-on-one contact in person, by phone, email, letter or fax. Appropriate follow-up will be provided to those in need. |  |  |  |
| 3. All senior-line calls will be answered by the ASCOG I&A. Call documentation will be made into AIM. |  |  |  |
| 4Any I&A hired will be AIRS/AD certified within one year. |  |  |  |
| 5. ASCOG staff will forward completed assessment forms and time sheets designating time worked on Access Services to ASCOG administrative staff for review. |  |  |  |
| 6. ASCOG will enter the units of service into AIM via a data entry clerk. |  |  |  |
| 7. ASCOG will submit reports as requested to ASD. |  |  |  |
| 8. ASCOG staff will mail out surveys to approximately 15% of participants who are randomly selected. |  |  |  |

| 1. SERVICE AREA INCLUDES THE FOLLOWING COUNTIES: |  |  |  |
| --- | --- | --- | --- |
| Caddo, Comanche, Cotton, Grady, Jefferson, McClain, Stephens & Tillman |  |  |  |
| II. NAME OF SERVICE: |  |  |  |
| Education/Information and Assistance for SFY 2018 |  |  |  |
| III. (A) $ Unit Cost | (B) $ Total Funding | (C) # Units | (D) Unduplicated Persons Served |
| $88.06 | $2,642 | 30 |  |
| IV. Formula used to calculate unit cost: |  |  |  |
| $2,642 total funding divided by 30 units of service = $88.06 per unit. |  |  |  |
| V. Show the breakdown of Total Funding for Service: |  |  |  |
| 30 units multiplied by $88.06 per unit = $2,642. |  |  |  |
| VI. Activities to Meet the Scope of Work: |  |  |  |
| 1. ASCOG will market all Supportive Services and Title III programs through public presentations, brochures, fliers, email blasts, press releases, blogs and letters to focal points. |  |  |  |
| 2. ASCOG staff will ask those in attendance at public presentations to complete sign-in sheets to document the presentation. |  |  |  |
| 3. ASCOG staff will document other types of marketing through copies of emails, press releases and fliers, along with a list of those to whom the marketing materials were sent. |  |  |  |
| 4. Prospective participants who respond to the marketing will be referred to the appropriate case manager or will receive an immediate assessment for services if possible. |  |  |  |
| 5. ASCOG staff will forward sign-in sheets, emails or other documentation and time sheets designating time worked on Education/Information and Assistance to ASCOG administrative staff for review. |  |  |  |
| 6. ASCOG will enter the units of service into AIM via a data entry clerk. |  |  |  |
| 7. ASCOG will submit reports as requested to ASD. |  |  |  |
| 8. ASCOG staff will email needs assessment surveys to all available contacts in the PSA. |  |  |  |

| 1. SERVICE AREA INCLUDES THE FOLLOWING COUNTIES: |  |  |  |
| --- | --- | --- | --- |
| Caddo, Comanche, Cotton, Grady, Jefferson, McClain, Stephens & Tillman |  |  |  |
| II. NAME OF SERVICE: |  |  |  |
| Information and Assistance for SFY 2017 |  |  |  |
| III. (A) $ Unit Cost | (B) $ Total Funding | (C) # Units | (D) Unduplicated Persons Served |
| $63.75 | $17,212 | 270 | 200 |
| IV. Formula used to calculate unit cost: |  |  |  |
| $17,212 total funding divided by 270 units of service = $63.75 |  |  |  |
| V. Show the breakdown of Total Funding for Service: |  |  |  |
| 270 units of service multiplied by $63.75 equals $17,212. |  |  |  |
| VI. Activities to Meet the Scope of Work: |  |  |  |
| 1. ASCOG will market the Information and Assistance programs through public presentations, brochures, fliers, email blasts, press releases, blogs and letters to focal points. |  |  |  |
| 2. ASCOG will ensure that an approved 02AG002E Older Americans Act Assessment (modified for I&A) is completed for each eligible participant who contacts or is referred to the Information and Assistance Specialist (I&A). The I&A service is a one-on-one contact in person, by phone, email, letter or fax. Appropriate follow-up will be provided to those in need. |  |  |  |
| 3. All senior-line calls will be answered by the ASCOG I&A. Call documentation will be made into AIM. |  |  |  |
| 4. Participants requesting options counseling will receive that service through the trained and certified I&A. |  |  |  |
| 5. ASCOG staff will forward completed assessment forms and time sheets designating time worked on Access Services to ASCOG administrative staff for review. |  |  |  |
| 6. ASCOG will enter the units of service into AIM via a data entry clerk. |  |  |  |
| 7. ASCOG will submit reports as requested to ASD. |  |  |  |
| 8. ASCOG staff will mail out surveys to approximately 15% of participants who are randomly selected. |  |  |  |

| 1. SERVICE AREA INCLUDES THE FOLLOWING COUNTIES: |  |  |  |
| --- | --- | --- | --- |
| Caddo, Comanche, Cotton, Grady, Jefferson, McClain, Stephens & Tillman |  |  |  |
| II. NAME OF SERVICE: |  |  |  |
| Education/Information and Assistance for SFY 2017 |  |  |  |
| III. (A) $ Unit Cost | (B) $ Total Funding | (C) # Units | (D) Unduplicated Persons Served |
| $88.06 | $2,642 | 30 | N/A |
| IV. Formula used to calculate unit cost: |  |  |  |
| $2,642 total funding divided by 30 units of service$88.06 per unit. |  |  |  |
| V. Show the breakdown of Total Funding for Service: |  |  |  |
| 30 units multiplied by $88.06 per unit = $2,642. |  |  |  |
| VI. Activities to Meet the Scope of Work: |  |  |  |
| 1. ASCOG will market all Supportive Services and Title III programs through public presentations, brochures, fliers, email blasts, press releases, blogs and letters to focal points. |  |  |  |
| 2. ASCOG staff will ask those in attendance at public presentations to complete sign-in sheets to document the presentation. |  |  |  |
| 3. ASCOG staff will document other types of marketing through copies of emails, press releases and fliers, along with a list of those to whom the marketing materials were sent. |  |  |  |
| 4. Prospective participants who respond to the marketing will be referred to the appropriate case manager or will receive an immediate assessment for services if possible. |  |  |  |
| 5. ASCOG staff will forward sign-in sheets, emails, other documentation and time sheets designating time worked on Education/Information and Assistance to ASCOG administrative staff for review. |  |  |  |
| 6. ASCOG will enter the units of service into AIM via a data entry clerk. |  |  |  |
| 7. ASCOG will submit reports as requested to ASD. |  |  |  |
| 8. ASCOG staff will email needs assessment surveys to all available contacts in the PSA. |  |  |  |

SFY17services include chore, home delivered meals, congregate meals, nutrition counseling, transportation, legal assistance and education, nutrition education, information and assistance, outreach, education and training, education information and assistance, health promotion, coordination of services, information about service caregivers, information about grandparents raising grandchildren services, assistance with access to service caregivers, assistance with access to grandparents raising grandchildren services, support groups for caregivers, support groups for grandparents raising grandchildren, respite caregivers and respite grandparents raising grandchildren.  Due to budget constraints and expected budget reductions, ASCOG does not plan to add any additional Title III services for SFY18.

In SFY17 and SFY18, ASCOG will not allow any Title IIIE funding for supplemental services because the demand for respite care is too high.  ASCOG will limit the GRRC program to 10% of Title IIIE funding.

ASCOG is currently using only Tier III CDSMP, evidenced-based programs for Title IIID funding through MaddieLuke.  MaddieLuke is also looking for additional Tier III programs and may submit Title IIID funding for those Tier III programs only after ASCOG and SUOA have approved those programs.

In SFY 16, (add SFY17/SFY18)ASCOG brought registered dietician services to the AAA level.  ASCOG continues this in SFY17 and will continue this services as a direct services in SFY18.  In SFY17 and SFY18, ASCOG will continue to mail out nutrition education material to all nutrition sites for monthly presentations.  Nutrition education materials will continue to be provided by the ASCOG registered dietician.  ASCOG will continue to record the units of nutrition education into AIM based on sign-in sheets returned from the nutrition sites.  Nutrition counseling will also continue to be provided by the ASCOG registered dieticians.  The dieticians check will continue to check with each site, bimonthly, to see if there are additional nutrition counseling referrals.  They will continue to also ask participants at the site if they would like a one-on-one session during their bimonthly presentations.  ASCOG RD’s will continue to conduct bimonthly S74 report assessments for each site.

| I. Service area includes the FOLLOWING COUNTIES: Stephens, McClain, Grady, Caddo, Comanche, Tillman, Cotton, and Jefferson counties |  |  |  |
| --- | --- | --- | --- |
| II. NAME OF SERVICE: NUTRITION EDUCATION |  |  |  |
| III. (A) $ Unit Cost | (B) $ Total Funding | (C) # Units | (D) Unduplicated Persons Served |
| $0.51 | $3,600 | 7,000 | 1,050 |
| IV. Detailed activities to Meet the Scope of Work |  |  |  |
| 1. ASCOG will provide the Nutrition Education program monthly through public presentations to congregate meal participants, brochures and fliers to home-delivered participants, email blasts, press releases, blogs and letters to focal points in the planning and service area. One unit of service is equal to one presentation or nutrition education material handout via mail, in-person, etc. |  |  |  |
| 2. ASCOG will ensure the Nutrition Education program materials are developed and written by the ASCOG AAA Registered Dietician. |  |  |  |
| 3. ASCOG will coordinate with nutrition project staff and volunteers to ensure each home-delivered meal recipient also receives a monthly nutrition education flier. |  |  |  |
| 4. ASCOG will ensure all eligible participants go through the intake process using the Title III Pilot Outreach forms and will update these forms annually. |  |  |  |
| 5. The RD will submit the nutrition fliers and time sheets to ASCOG for review and payment. |  |  |  |
| 6. ASCOG will enter the units of service into AIM via a data entry clerk. |  |  |  |
| 7. ASCOG will submit reports as requested to ASD. |  |  |  |
| 8. ASCOG staff will mail out surveys annually to all participants who have received nutrition education services. |  |  |  |

| II. NAME OF SERVICE: NUTRITION COUNSELING |  |  |  |
| --- | --- | --- | --- |
| III. (A) $ Unit Cost | (B) $ Total Funding | (C) # Units | (D) Unduplicated Persons Served |
| $50.33 | $3,276 | 60 | 60 |
| IV. Detailed activities to Meet the Scope of Work |  |  |  |
| 1. ASCOG will provide the Nutrition Counseling program through individualized guidance to a participant. ASCOG will market the program to congregate meal participants, brochures and fliers to home-delivered participants, email blasts, press releases, blogs and letters to focal points in the planning and service area. One unit of service is equal to one counseling session that is provided one-on-one by a registered dietician. |  |  |  |
| 2. ASCOG will ensure the Nutrition Counseling program materials are developed and written by the ASCOG AAA Registered Dietician. |  |  |  |
| 3. ASCOG will coordinate with nutrition project staff and volunteers to ensure each home-delivered meal recipient is aware of the Nutrition Counseling program. |  |  |  |
| 4. ASCOG will ensure all eligible participants requesting Nutrition Counseling receive the service by the RD. |  |  |  |

## EXHIBIT 16. DISASTER PLAN/IMMUNIZATIONS

The Association of South Central Oklahoma Governments has a Director of Public Safety who helps take the lead in disaster situations.  Safety training is provided to staff on an annual basis.  ASCOG’s Public Safety Director works with regional emergency managers in addressing local disasters, formal and informal communications and addressing the needs of at-risk populations.

When a disaster occurs, ASCOG staff attempts to contact frail citizens to ensure they are safe.  If they are unable to contact them, then the emergency management coordinator is to contact a public safety officer to conduct a welfare check.

ASCOG is prepared for business continuity through use of off-site data management and backup, VOIP communication as well as cloud-based computing programs.  Should a natural disaster hit the ASCOG main office, the majority of ASCOG staff would be fully functional within hours.

ASCOG provides Title III-D Health Promotion activities through evidence-based programs like the Chronic Disease Self-Management Program and Tai Chi.

The ASCOG AAA will ensure and advocate for the coordinated vaccination of seniors, particularly for influenza and pneumonia, through the Advocate blog, presentations and brochures.

## EXHIBIT 17. COORDINATION ACTIVITIES BETWEEN TITLE III AND TITLE VI

Within the ASCOG Planning and Services Area, there are several Native American service providers.  The Caddo Nation, the Chickasaw Nation the Comanche Nation, the Wichita and affiliated tribes, the Kiowa Tribe, the Fort Sill Apache Tribe and the Delaware Nation are all service providers in the ASCOG area.

In SFY17, ASCOG added to the first quarterly assessment to review each project to ensure coordination is occurring between all Title III providers and tribal governments.  ASCOG visits the Choctaw and Fort Sill Apache tribes annually to coordinate services and to invite tribal leadership to become members of the ASCOG Advisory Council.

In SFY17, ASCOG Charity Helms from the Fort-Sill Apache Tribe to be a member of the ASCOG AAA Advisory Council.  She replaces the late Kenneth Saupitty, also of that tribe.  Additionally, ASCOG continues to require attempts from each Title III subcontractor to establish memoranda of understanding with the tribes local to their respective service areas.

## EXHIBIT 18. LONG RANGE PLAN

ASCOG AAA expects dramatic changes in the needs of seniors as the surviving population from the World War II Generation declines and the Baby Boomers continue to retire.  Boomers are expected to spend less time in senior centers and more time in intergenerational activities.  Boomers have a more difficult time discussing end of life issues and planning for retirement.  According to a 2011 Associated Press and LifeGoesStrong.com surveys, 60% of boomers lost value in investments because of economic crisis, 42% are delaying retirement and 25% claim they’ll never retire.  The common retirement age as of 2013 is 67 years old.  1,2

The caregivers of Boomers (born 1946 through 1964) tend to be much more computer literate and use social media as a matter of course.

ASCOG AAA expects to gradually move more OAA funding from senior center focused services to home-based services.

ASCOG also expects more services to be provided through online interactions.  Already ASCOG AAA regularly publishes a blog called the ASCOG Advocate as well as posts on Facebook, Twitter and LinkedIn.

ASCOG AAA has already begun to focus on mental health treatment and screenings.  Mental Health screenings have been added to the health promotion services using Title III-B dollars in the 2015 RFP package.  Outreach is also performed on a regular basis using mental health screenings and referrals. ASCOG AAA will continue to focus on mental health by educating participants in the PSA and by finding and developing community partners that are related to and offer services for mental health issues.

Because of the nationwide trend in Medicaid managed care, ASCOG is currently working with other ADvantage providers and through the Oklahoma Association of Area Agencies on Aging to ensure ADvantage services and other long-term care services and supports are provided via a statewide strategy.

- ^ "Retirement? For More Baby Boomers, The Answer Is No". ThirdAge Staff. Archivedfrom the original on July 21, 2011. Retrieved June 6, 2011.

- Jump up^ "Redefining Retirement: A Much Longer Lifespan means more to Consider". Living Better at 50. Retrieved August 17, 2011.

## EXHIBIT 19. COMMERCIAL OR CONTRACTUAL ACTIVITIES

The quality of OAA services provided by ASCOG AAA has been enhanced by the performance of ADvantage services.  A portion of the AAA Director salary is paid by the Advantage services.  The full salary of the Deputy Director of Supportive Services is paid by ADvantage.

ASCOG provides the ADvantage program through a contract with the ADvantage Administration Unit of DHS Aging Services.

ASCOG provides the Community Expansion Nutrition Assistance grant through a contract with the Oklahoma Department of Commerce.

ASCOG provides the Masonic Charities Foundation Grant through a contract with the Oklahoma Masonic Charities Foundation via the Oklahoma Association of Area Agencies on Aging.

ASCOG provides the Senior Health Insurance Program grant services through a contract with the Oklahoma Insurance Department.

ASCOG provides the Senior Community Services Employment Program through a contract with DHS Aging Services, SUOA.

ASCOG AAA maintains the integrity and public purpose of OAA services while performing contract services.

OAA funds are not used in any part of the cost of contract services, including administrative cost.

Preference will not be given to contract services clients in receiving Title III services provided in the ASCOG area.

ASCOG will account for the contract services funds according to generally accepted accounting and auditing practices.

ASCOG will make available accounting and auditing practices of contract services activities for review by DHS Aging Services.

ASCOG conducts the following commercial services:

ENTITY          SERVICES                  FUNDING SOURCE      COUNTY

SERVED

ADvantage      Case Management           Federal Title XIX            Caddo

ADvantage      Case Management           Federal Title XIX       Comanche

ADvantage      Case Management           Federal Title XIX            Cotton

ADvantage      Case Management           Federal Title XIX            Grady

ADvantage      Case Management           Federal Title XIX         Jefferson

ADvantage      Case Management           Federal Title XIX          McClain

ADvantage      Case Management           Federal Title XIX         Stephens

ADvantage      Case Management           Federal Title XIX           Tillman

CENA              Nutrition Assistance    OK Dept of Commerce   Caddo

CENA              Nutrition Assistance    OK Dept of Commerce Comanche

CENA              Nutrition Assistance    OK Dept of Commerce  Cotton

CENA              Nutrition Assistance    OK Dept of Commerce   Grady

CENA              Nutrition Assistance    OK Dept of Commerce  McClain

CENA              Nutrition Assistance    OK Dept of Commerce Jefferson

CENA              Nutrition Assistance    OK Dept of Commerce  Stephens

CENA              Nutrition Assistance    OK Dept of Commerce  Tillman

MAP                Medicare                           OID                              Harmon

MAP                Medicare                           OID                                Greer

MAP                Medicare                           OID                              Jackson

MAP                Medicare                           OID                                Kiowa

MAP                Medicare                           OID                              Tillman

MAP                Medicare                           OID                             Comanche

MAP                Medicare                           OID                              Stephens

MAP                Medicare                           OID                                Cotton

MAP                Medicare                           OID                             Jefferson

MAP                Medicare                           OID                                Garvin

SMP                 Medicare                           OID                              Harmon

SMP                 Medicare                           OID                                Greer

SMP                 Medicare                           OID                              Jackson

SMP                 Medicare                           OID                                 Kiowa

SMP                 Medicare                           OID                              Tillman

SMP                 Medicare                           OID                            Comanche

SMP                 Medicare                           OID                              Stephens

SMP                 Medicare                           OID                                Cotton

SMP                 Medicare                           OID                              Jefferson

SMP                 Medicare                           OID                                 Garvin

MIPP               Medicare                           OID                               Harmon

MIPP               Medicare                           OID                                  Greer

MIPP               Medicare                           OID                               Jackson

MIPP               Medicare                           OID                                 Kiowa

MIPP               Medicare                           OID                               Tillman

MIPP               Medicare                           OID                             Comanche

MIPP               Medicare                           OID                               Stephens

MIPP               Medicare                           OID                                 Cotton

MIPP               Medicare                           OID                              Jefferson

MIPP               Medicare                           OID                                 Garvin

Masonic           Unmet Needs                   OMCF                              Caddo

Masonic           Unmet Needs                   OMCF                         Comanche

Masonic           Unmet Needs                   OMCF                             Cotton

Masonic           Unmet Needs                   OMCF                             Grady

Masonic           Unmet Needs                   OMCF                           McClain

Masonic           Unmet Needs                   OMCF                          Jefferson

Masonic           Unmet Needs                   OMCF                          Stephens

Masonic           Unmet Needs                   OMCF                           Tillman

SCSEP	             Senior Employment        OKDHS                	  Beckham

SCSEP	             Senior Employment        OKDHS                	  Cleveland

SCSEP	             Senior Employment        OKDHS                	  Cotton

SCSEP	             Senior Employment        OKDHS                	  Custer

SCSEP	             Senior Employment        OKDHS                	  Greer

SCSEP	             Senior Employment        OKDHS                	  Harmon

SCSEP	             Senior Employment        OKDHS                	  Jackson

SCSEP	             Senior Employment        OKDHS                	  Jefferson

SCSEP	             Senior Employment        OKDHS                	  Kiowa

SCSEP	             Senior Employment        OKDHS                	  McClain

SCSEP	             Senior Employment        OKDHS                	Roger Mills

SCSEP	             Senior Employment        OKDHS                	  Stephens

SCSEP	             Senior Employment        OKDHS                	  Tillman

SCSEP	             Senior Employment        OKDHS                	  Washita

# PART F.  FINANCIAL MANAGEMENT PLAN

## EXHIBIT 20. AREA PLAN BUDGET JUSTIFICATION

Use Section C of Resource Allocation Memo to Complete.

| AREA AGENCY ON AGING |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | TOTAL |
| PERSONNEL AAA Director, Ken Jones $20,632 AAA Accountant, Nancy Bluml $16,205 I&A, Kris Brown $17,887 ASCOG Executive Director, Ronnie Ward $1,749 ASCOG Financial Officer, Robert Denard $2,311 Fringe @69.50% $47,679 |  |  |  |  |  |  |
| TOTAL PERSONNEL/FRINGE |  |  |  | $106,463 |  |  |
| TRAVEL Staff 8,510 miles at $.47/mile $4,354 Advisory Council and Advocacy volunteer travel $3,000 |  |  |  |  |  |  |
| TOTAL TRAVEL |  |  |  | $7,354 |  |  |
| EQUIPMENT |  |  |  |  |  |  |
| TOTAL EQUIPMENT |  |  |  |  |  | $0.00 |
| OTHER Professional Dues $1,000 Registration $400 Printing $2,600 Contract Services $13,751 Telephone $3,500 Consumable supplies $1,900 Postage $2,400 |  |  |  |  |  |  |
| TOTAL OTHER COST |  | $25,551 |  |  |  |  |
| INDIRECT COSTS @23.19% $32,319 |  |  |  |  |  |  |
|  | TITLE III FUNDING |  | GRANTEE |  | TOTAL |  |
| TOTAL AAA COSTS | $159,403 |  | $12,285 |  | $171,688 |  |

FINANCIAL MANAGEMENT PLAN

## EXHIBIT 21. OMBUDSMAN BUDGET JUSTIFICATION

| AREA AGENCY ON AGING |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | TOTAL |
| PERSONNEL OMBUDS VOLUNTEER SUPERVISOR I ($27,739) Darin Terry $24,322 OMBUDS VOLUNTEER SUPERVISOR I ( $27,739) Dacia Nix $24,322 FRINGE 39,230 |  |  |  |  |  |  |
| TOTAL PERSONNEL/FRINGE |  |  |  | $87,874 |  |  |
| TRAVEL OMBUDS VOLUNTEER SUPERVISOR I $2,000 OMBUDS VOLUNTEER SUPERVISOR I $2,000 Volunteer Ombudsmen $1,000 |  |  |  |  |  |  |
| TOTAL TRAVEL |  |  |  | $5,000 |  |  |
| EQUIPMENT |  |  |  |  |  |  |
| TOTAL EQUIPMENT |  |  |  |  |  | $0.00 |
| OTHER |  |  |  |  |  |  |
| TOTAL OTHER COST |  |  |  |  |  | $0.00 |
| INDIRECT COSTS ** $21,537 |  |  |  |  |  |  |
|  | TITLE III FUNDING |  | GRANTEE |  | TOTAL |  |
| TOTAL AAA COSTS | $106,224 |  | $8,187 |  | $114,411 |  |

*Use Exhibit 25 OKDHS Job Family Descriptors for Ombudsmen Provided in this FMP.

**Direct Costs may not be included in Indirect Costs.

FINANCIAL MANAGEMENT PLAN

## EXHIBIT 22. SUMMARY OF PROCESS USED TO AWARD FUNDS

Use this section to comply with Title III OAC Policies 340:105-10-33, 101, and 40 requiring documentation of the AAA's Process Used to Award Funds.

ASCOG AAA prepares a request for proposals package for all available services.

The RFP is published in three area newspapers, one in Lawton, one in Duncan and one in Chickasha.  The RFP is published on two different dates, at least three weeks prior to the deadline for proposals.  A mandatory proposers’ conference is also held.  All technical assistance is provided by publication to our website or in conference with all applicants to ensure fairness.  Proposals are reviewed and scored by ASCOG staff using an objective scoring system approved by the ASCOG Board of Trustees Executive Committee.  The scores are then presented to the ASCOG AAA Advisory Council for review and comment.    The recommendations of the advisory council are then presented to the ASCOG Board of Trustees.

Documentation of the publishing of the RFP is maintained by the ASCOG

An appeals process is conducted should an applicant wish to appeal the decision of the RFP process.

Should a proposal not be accepted by the ASCOG AAA Advisory Council or the Board of Trustees, then the proposal will be sent a letter of rejection.

In the event no proposals are accepted and approved by ASCOG, then a new Request for Proposal is submitted.  During the secondary RFP, teleconferencing will be allowed for the proposers’ conference to allow for companies outside of the ASCOG PSA to attend via teleconference.

## EXHIBIT 23. NEGOTIATED AGREEMENT FOR INDIRECT COSTS

## EXHIBIT 24. INDIRECT COST RATE PROPOSAL

ASCOG’s indirect costs are calculated by using the OMB Circular A-87 guidelines outlined in Attachment E. Indirect costs are allocated by using a predetermined budgeted rate which is calculated yearly. The indirect rate is calculated by taking budgeted indirect costs and dividing them by the modified total direct cost base – modified total direct cost excludes pass-through funding, in-kind expenses, and participant salaries. Indirect costs are allocated to our grant programs each month using actual indirect costs and actual modified total direct costs. Additionally, we use a fiscal year to date allocation each month to ensure that indirect costs are distributed evenly across all twelve months.

## EXHIBIT 25. OKDHS JOB FAMILY DESCRIPTORS FOR OMBUDSMAN

| Job Family Descriptor | Monthly Hiring Range | Yearly Hiring Range | OPM Monthly Midpoint | OPM Monthly Maximum |
| --- | --- | --- | --- | --- |
| Adult Protective Services Specialist I | $2,275.24 - $2,717.04 | $27,302.88 - $ 32,604.48 | $2,944.68 | $3,680.86 |
| Adult Protective Services Specialist II | $2,516.38- $2,987.02 | $30,196.56- $35,844.24 | $3,237.38 | $4,046.72 |

OKDHS data as of Oct 16, 2013 thru Jan 15, 2014.

See OAC policy 340:105-11-249 and 340:105-11-250.

Revised  1/28/2014

Director, Supportive Services Division

Under the general supervision of the executive director, the director plans, coordinates, administers and evaluates activities involving the development and implementation of comprehensive area planning for all older persons throughout the ASCOG area.

Duties and Responsibilities:

1.	Provide leadership and advocacy on behalf of all older persons within the planning and service area for which ASCOG is responsible.

2.	Supervise, coordinate, evaluate and monitor all other ASCOG administered aging programs, staff and activities to include managed care services.

3.	Assume full responsibility for all functions of the ASCOG-administered aging programs within the guidelines and regulations of the Older Americans Act and other federal and state agencies.

4.	Establish measurable program objectives and priorities for implementation of the Area Plan, in keeping with the objectives established by the state agency.

5.	Establish and maintain an Area Agency on Aging (AAA) Advisory Council.  Provides data and pertinent information on the elderly in the planning and service area.

6.	Coordinate the activities of the AAA, to include managed care services, with other agencies involved in delivery of services for the elderly and pool available but untapped resources of public and private agencies in order to strengthen or initiate new services for older persons.

7.	Maintain liaison with the Special Unit on Aging of the Oklahoma Department of Human Services and other applicable state and federal agencies.

8.	Serve as a consultant to community organizations and agencies on program development, techniques of working with older people, sources of program support and the solution of special problems.

9.	Promote good public relations through public speaking and through effective relationships with mass media personnel.

10.	Perform or supervise administrative functions necessary for the AAA's operation, such as record keeping and budgeting.

11.	Conduct periodic public hearings concerning the needs of the elderly.

12.	Provide training and technical assistance to Title III project staff under the Area Plan on a regular basis.

13.	Negotiate grants and contracts for various programs for the elderly.

Chair the ASCOG personnel committee.  Recommend personnel policies and procedures consistent with state and federal laws and good management practices.  Assure fairness of policies and implementation.

17.	Serve as Equal Opportunity Officer for the organization.

- 18.	Perform other duties as assigned.

Skills and Knowledge:

Considerable knowledge of (1) modern methods and principles of planning for older citizens, (2) the basic principles of administration, (3) community services and organizations concerned with older citizens and their interrelationships and (4) the demographic, environmental, social and economic characteristics of the State.

Ability to  (1) enlist and support of diverse groups within local communities, (2) mobilize latent community support, including cooperation of the mass media, professional groups and industrial development commissions, (3) plan, organize and coordinate activities of local committees on aging for the development and promotion of community education and planning programs, (4) supervise and train professional and non-professional workers, (5) summarize factual data succinctly and to present it in writing and speeches so that it is clearly understood by State and community leaders. (6)  prepare reports and (7) use sound judgment in evaluating administrative problems, situations and in making effective recommendations.

Considerable knowledge of government functions, local and regional planning process, evaluation of needs, and implementation of solutions.

Education and Experience:

A degree from an accredited college or university with major course work in any of the following fields: public administration, planning, community organization, social work, social sciences, adult education, public health, human relations, gerontology, or related field.  (A graduate degree is preferred.) Three years of responsible full-time paid employment in a public agency, hospital, community agency or other closely related area of social services in a supervisory or administrative capacity

OR

One (1) year of qualifying experience may be substituted for each year of required education with a maximum substitution of two (2) years.

Salary Range:

Grade 80:	$43,642 - $58,567

| Job Family Descriptor | Monthly Hiring Range | Yearly Hiring Range | OPM Monthly Midpoint | OPM Monthly Maximum |
| --- | --- | --- | --- | --- |
| Programs Manager | $3,926.38-$4,434.80 | $47,116.56-$53,217.60 | $4,795.85 | $5,994.81 |

Information & Assistance/Aging Specialist

The Aging Information Assistance/Aging Specialist provides information and referral services for older persons in the ASCOG area; and assists the AAA Director in the implementation of the AAA program.

Duties and Responsibilities:

a.	Works under the direct supervision of the Area Agency Director, obtaining data, answering the telephone and responding to requests for information and referral.

b.	Knows the minimum requirements of the AOA for I and R services and assures compliance with them.

c.	Responsible for resource data collection and proper maintenance and updating of resource materials and files.

d.	Maintains contact with the public, including resource agencies and aging programs.

e.	Compiles and submits reports.

f.	Conducts publicity campaigns to publicize the service.

g.	Recruits and trains volunteers for advocacy outreach and follow-up.

h.	Is knowledgeable about the general functions of the AAA,  performs other duties and responsibilities to help support the AAA and staff.

i.	Individual must become certified and have the ability to administer and work with the	Older Americans Act Assessment

j.	Develops handouts and/or brochures.

k.	Provides literature to community groups and aging programs.

l.	Informs AAA staff regarding gaps in services.

m.	Must be intake/screener certified in the use of OKDHS Form AF-2-A, Older Americans Act Assessment; maintain client confidentiality/ and be willing and able to perform job-related travel.

n..	Serves as ASCOG Public Information Officer.

o.	Attends Trustee meetings and writes press releases.

p.	Performs other duties as assigned by the AAA Director and Executive Director.

Education and Experience:

Graduation from an accredited four year college or university with major course work in public relations, social sciences, gerontology, administration or related field.  One year of responsible full time paid employment in such fields as adult education, community organization, public relations, public health, social work, or related field.  Knowledge of the needs of older persons and the aging network is preferred.

Bachelors’ Degree required.  Work experience is preferred but may be substituted by equivalent graduate education.

Salary Range:

Grade 48:  $20,801 - $27,739

| Job Family Descriptor | Monthly Hiring Range | Yearly Hiring Range | OPM Monthly Midpoint | OPM Monthly Maximum |
| --- | --- | --- | --- | --- |
| Public Information Officer /I&A | $2,542.65-$2,717.04 | $30,511.80-$32,604.48 | $2,944.68 | $3,680.86 |

Ombudsman Supervisor

Under the general direction of the Director of the ASCOG Area Agency on Aging, provides leadership in development, coordination, and implementation of the Long-Term Care Ombudsman Program.  Receives, investigates and resolves complaints made by or on behalf of residents of long-term care facilities.

Duties and Responsibilities:

1.	Recruits, screens, trains and supervises ombudsman volunteers, using guidelines provided by State Ombudsman staff.

2.	Publicizes the services of the Ombudsman Program and issues affecting older residents of long-term care facilities through media releases, public speaking and other means.

3.	Coordinates with State Ombudsman staff in complaint investigation and resolution, identification of priority issues and certification of new ombudsman volunteers.

4.	Maintains confidentiality of files and other information pertaining to complaints and complainants.

5.	Keeps Director informed of the current situation and needs at the local level, recommends plans for meeting needs, and advises him/her of resources required for their implementation.

6.	Is available to residents of long-term care facilities in the PSA, visiting each facility regularly and working cooperatively with administrators and staff.

7.	Serves as a consultant to community organizations and agencies on issues and needs affecting older long-term care facility residents, techniques of working with these older people, and the solution of special problems. Offers education to facility staff through in-service training and technical assistance.

Education and Experience:

Graduation from an accredited four year college or university with major course work in social work, health, gerontology, general social sciences or related field

OR

an equivalent combination of education and experience substituting one (1) year of full time paid experience in such areas as community organization, public health, social work or related field for each year of the required education with a maximum substitution of two (2) years.

Salary Range:

Grade 47:   $23,441 - $31,277

Accountant II/Resource Management/Area Agency On Aging

Works under general supervision of the Director of Resource Management and coordinates with the AAA Director, performs accounting work for the Association and Area Agency on Aging; performs related work as required.

Duties and Responsibilities:

- Reviews AAA vendor invoices and travel claims for accuracy and classifies the expenditures according to the budget and chart of accounts.  Processes monthly subgrantee vouchers and prepares monthly distributions to subgrantees.

- Creates and maintains project expenditure reports for AAA grants.  Reports to grantor agencies and management on the financial activities and status of grants.

- Makes regular on-site visits to AAA sub-grantees to monitor financial activities, record keeping, and compliance. Attends annual audits for subgrantees, if requested.  Serves as the AAA financial resource at Advisory Council meetings.

- Reviews financial reports submitted by AAA sub-grantees to ensure accuracy.  Compiles sub-grantee reports for submission to grantor agency.

- Provides technical assistance in accounting and bookkeeping functions to sub-grantees on a regular and continuing basis to resolve financial, personnel, and policy issues.  Reviews subgrantees preparation of budget and develops AAA Admin budget.

- Serves as Accounts Receivable Clerk.  Receives and codes all receipts into the agency including recording transactions in the computer system and preparing daily bank deposits.

- Serves as Inventory Clerk.  Coordinates furniture and equipment inventory and maintains official inventory listing.

- Conducts and arranges for training of project staff.

- Monitors and assesses funded programs and projects. May develop and revise assessment tools for this purpose.

- Assists the AAA director in development of the Area Plan.

- Assists the AAA director in the administration of the Community Expansion for Nutrition Assistance (CENA) grant.

- 12.  	Performs other related work as required and assigned.

Skills and Knowledge:

General knowledge of professional accounting theory and practice; of elementary auditing principles and methods; of office procedures and methods; of professional accounting terminology and phraseology; of standardized records, reports; of arithmetical computation of analytical and evaluation procedures.  Knowledge of Federal Standards.

Ability to establish and maintain satisfactory and effective working relationships with others; to follow relatively complex and difficult oral and written instruction and/or accounting procedures; all as evidenced by an investigation and/or an oral interview.

Education and Experience:

Graduation from an accredited college or university with a Bachelors’ Degree in accounting or a Bachelors’ Degree in business, finance or a closely related field.  Substitution of work experience in accounting field of at least four years may be allowed for the Bachelor’s degree.

Salary Range:

Grade 58:  $25,803 - $34,411

| Job Family Descriptor | Monthly Hiring Range | Yearly Hiring Range | OPM Monthly Midpoint | OPM Monthly Maximum |
| --- | --- | --- | --- | --- |
| Accountant II/AAA Accountant | $2,968.56-$3,143.08 | $35,622.72-$37,716.96 | $3,237.38 | $4,046.72 |

# PART G.  AREA PLAN APPENDICES

- Organizational Chart- AAA

- Organizational Chart- Sponsoring Agency

- Area Agencies on Aging Responsibilities

- AAA Advisory Council

- AAA Advisory Council Schedule of Meeting & Training Dates

- AAA Board of Directors

- AAA Board of Directors Schedule of Meeting Dates

- Training Schedule- AAA Staff and Annual Project Training

- Administration for Community Living Strategic Goals 2013-2018

- Designated Focal Points

- Aging Program Output Narrative

- Projected Aging Program Output Numerical

- Demographics of Older Persons in PSA

- List Non-Title III Services in PSA

- Current Poverty Guidelines

- Management Plan Narrative

- Indirect Cost Rate Proposal

- Public Hearing Summary and Changes, if any made to AP

- Advisory Council Summary and Changes, if any made to AP

- AAA Board of Directors Summary and Changes, if any made to AP

APPENDIX 1. ORGANIZATIONAL CHART- AAA

ASCOG AAA

* Director

Ken Jones, 50%

Part-time Secretary

Sheri Cathey, contract

Accountant II

Nancy Bluml, 70%

Ombudsman

Dacia Nix

I & A Specialist

Kristina Brown, 70%

Ombudsman

Darin Terry

* Same person is ASCOG Supportive Services Division Director

APPENDIX 2. ORGANIZATIONAL CHART- SPONSORING AGENCY

Association of South Central

Oklahoma Governments

Organizational Chart

Cities, Towns, Counties, & Conservation Districts

Board of Trustees

Executive Committee

Executive Director

Ronnie Ward

Resource Management Division

Robert Denard

Nancy English,

Deputy Director

Environmental Services Division

Stan Rice, Director

Public Safety & Analysis Division

Perry Brineger, Director

Community & Economic Development Division

Tom Zigler, Director

Supportive Services Division

* Ken Jones, Director

##### * Same person is ASCOG Area Agency on Aging Director

APPENDIX 3. AREA AGENCIES ON AGING RESPONSIBILITIES

The State agency utilizes eleven sub-state planning and service areas (PSA) for federal planning and has designated eleven area agencies on aging (AAA) in accordance with the requirements of Title III of the Older Americans Act (OAA). Each of the AAA has an advisory council to assist in assessing the needs of older persons within its geographic location and in developing a comprehensive system of services to meet these needs.

The major activities of each AAA are outlined in a four-year area plan with annual updates as necessary. Criteria for approval of the area plan include identification of priority needs, development of measurable objectives, and targeting of services to those in greatest economic or social need. The AAA in Oklahoma switched from the federal fiscal year to the state fiscal year in 2006 to comply with State agency financial management practices. The change will not impact the federal funding or reporting processes. It will however have a positive impact on state funding for the area agencies. AAA coordinate their activities with service agencies and organizations in order to avoid duplication of services. They also seek to involve the public and private sectors in the provision and expansion of services.

The provision of services is accomplished by the awarding of grants through a Request for Proposal process to local public or private entities. State policy is in place to ensure all OAA pass-through funds are awarded in an open, competitive, and fair process. Direct services otherwise prohibited by the OAA may be permitted by Aging Services Division (ASD) if, in the judgment of the State agency, provision of the services is:

(1) necessary to ensure an adequate supply of the services;

(2) related to the administrative functions of the area agency on aging (AAA); or

(3) more economical and of comparable quality.

It is the responsibility of the AAA to monitor project compliance with regulations and assurances within state policy and the OAA as well as to evaluate the effectiveness of services rendered to older people. The variety of services to be provided (as appropriate) under Titles III and VII includes but is not limited to:

I.	access services (transportation, outreach, information and assistance, and case management);

II.	in-home services (homemaker, personal care, and chore service);

III.	legal assistance;

IV.	nutrition services (congregate meals, home-delivered meals, nutrition counseling and nutrition education);

V.	Long-Term Care Ombudsman Program services; and

VI.	community support and social services (health promotion, adult day care,

respite, and home repair).

APPENDIX 4.  AREA AGENCY ON AGING ADVISORY COUNCIL

Composition of Advisory Council

| Total Members Advisory Council | Total Minority | Total with Disabilities | Total Caregivers | TOTAL Age 60+ | Advisory Council Members Who Are Age 60 Or Older |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | BLACK Age 60+ | HISPANIC Age 60+ | ASIAN Age 60+ | AMERICAN INDIAN Age 60+ | W/Disabilities Age 60+ | LOW INCOME Age 60+ | Participants Age 60+ |
| 25 | 4 | 2 | 1 | 24 | 2 | 1 | 0 | 1 | 2 | 2 | 24 |

| Name | Address/Phone Number | County Represented |
| --- | --- | --- |
| Marlene Walker Vice-Chair | 4622 Walker Road Hinton, OK 73047 405.929.0324 (cell) 405.542.3370 marmax1@hintonet.net | Caddo |
| Charity Helms | 43187 US HWY 281 Apache, OK 73006 580.288.2298 charity.helms@fortsillapache-nsn.gov | Caddo |
| Thelmer Hutcheson | 11 Goldenrod Way Lawton, OK 73507 580.585.0677 (cell) 580.529.3046 (home) jeanthel@gmail.com | Comanche |
| Charley Maguire | 23393 NE North Drive Fletcher, OK 73541 580.549.6470 ccmaguire@tds.net | Comanche |
| Petra Taylor | 1026 SW 61st Street Lawton, OK 73505 580.536.6477 (home) 580.574.5766 (cell) Petrataylor9@yahoo.com | Comanche; Cotton |
| Karolyn Anders | 127 NE Cimarron Lawton, OK 73507 580.351.8039 (cell) bkanders@fidnet.com | Comanche; Cotton |
| Louise Hamilton | 518 E. California Walters, OK 73572 580.695.5068 (home) | Cotton |
| Loretta Jackson | 322 E Dakota Avenue Chickasha, OK 73018 405.224.5297 (home) lyjackson1@suddenlink.net | Grady |
| Dorothy Moore | PO Box 95 Ryan, OK 73565 580.757.2730 (home) DotM@att.net | Jefferson |
| Rubye Benson Secretary | 804 Hillcrest Drive Waurika, OK 73573 580.228.2087 (home) 580.228.2080 (office) rubye79@sbcglobal.net | Jefferson |
| Lewie Jeffries | PO Box 742 Washington, OK 73093 405.760.1282 Lewiejeffries40@icloud.com | McClain |
| Rowena Scott-Johnson | 22157 220th Street Purcell, OK 73080 405.818.9659 (cell) 405.527.0853 (home) rojohn2@gmail.com | McClain |
| Sandy Stewart | 911 West Walnut Duncan, OK 73534 580.255.3644 | Stephens |
| J.M. Cope | PO Box 181 Frederick, OK 73542 580.335.2644 | Tillman |
| Watha Shanks | 920 S 13th St Frederick, OK 73542 580.335.5177 (home) | Tillman |
| Haljean Gillispie | 2912 West Walnut Duncan, OK 73533 580.656.3805 (cell) 580.475.0354 (home) haljean@sbcglobal.net | Grady, Jefferson, McClain & Stephens |
| Charles Watson | 1525 W. Mississippi Avenue Chickasha, OK 73018 405.222.1637 (home) 405.222.8195 okieparson@att.net | Grady |
| Merlene Rust Chair | PO Box 620 Rush Springs, OK 73082 405.820.6649 (cell) 580.476.3103 (office) merlenerust@yahoo.com | Grady & McClain |
| Ray Merchant | PO Box 322 Ninnekah, OK 73067 405.779.1817 (cell) 405.224.1391 (home) raymerchant@wichitaonline.net | Grady & McClain |
| (Vacant) |  | Comanche, Cotton & Tillman |
| John Kusel | PO Box 370 Fort Cobb, OK 73038 580.759.6038 (cell) kusellim@sbcglobal.net | Caddo; Tillman |
| Gloria Stearns | 18062 CR 1320 Anadarko, OK 73005 405-247-6040 (home) 405-933-0536. (cell) Stearnsgloria@gmail.com | Caddo |
| Katie Ebner | Gentiva Health Services 2210 W Gore Blvd, Suite 3 Lawton, OK 73501 580.248.9998 (office) katie.ebner@gentiva.com | Comanche |
| Lauren Ellis | United Way of Southwest Oklahoma PO Box 66 Lawton, OK 73502 580.355.0218 (office) Lauren.ellis@uwsok.org | Comanche |
| Oleta Butler | Respite Caregiver Program 2 SE Lee Blvd. Lawton, OK 73501 580.512.7758 (office) rcp@gpif-caa.org | Comanche |
| Jalmer “Bo” Fallon Treasurer | 7511 NW Wycliff Lane Lawton, OK 73505 Jalmer.Fallon@sbcglobal.net (personal) jfallon@fidmail.com (business) | Comanche; Tillman; Cotton & Caddo |

Purpose:  The Advisory Council carries the advisory functions which further carries out ASCOG’s mission of developing and coordinating community-based systems of services for all senior citizens within Caddo, Comanche, Cotton, Grady, Jefferson, McClain, Stephens and Tillman counties.

The membership of the council includes all members of the South Central Oklahoma caucus of the Silver Haired Legislature and the alternates, the ASCOG AAA representative to the state council on aging and three other members from each county as selected by mayoral, county commissioner representatives and members at large.

The advisory council is responsible for advising the ASCOG AAA in developing and administering the area plan, conducting public hearings, representing the interests of older persons and reviewing and commenting on all community policies, programs and actions which affect older persons to ensure the maximum coordination of services to older Oklahomans in the ASCOG planning service area (PSA).

Advisory Council members cannot be members of boards or staff of Title III projects, ASCOG staff or board members, or DHS staff.  If an advisory council member becomes a party to an applicant for a Title III grant, they will abstain from voting on grant funding.  If awarded the grant, they will no longer be on the advisory council.

Vacancies in AAAAC membership are filled by providing nominations to the county commissioner or mayoral representative on the ASCOG board.  ASCOG has minority representatives on the board who provide input into AAAAC recruitment.  ASCOG is currently recruiting a Hispanic member of the AAAAC as a Stephens county mayoral representative appointee.

Advisory council membership also includes elected or appointed members of the ASCOG Oklahoma Silver Haired Legislature.  Acting OSHL representatives and senators are voting members while their alternates are non-voting members.

Advisory council membership is also extended to tribal senior program representatives as non-voting members.  They can be voting members if appointed by a board member or elected to the OSHL.

APPENDIX 5.  ADVISORY COUNCIL SCHEDULE OF MEETING DATES

September 21, 2017

December 14, 2017

March 15, 2018

June 21, 2018

All meetings except for the March meetings are scheduled to be held at 10:00 a.m. at the Red River Technology Center, Jerry D. Morris Business and Industry Service Center, 3300 W. Bois D’Arc, Duncan, OK  73533. March meetings are scheduled at the Chisholm Trail Heritage Center at 1000 Chisholm Trail Drive in Duncan.  Both facilities are ADA accessible.

New member and annual training is provide annually before and during one of the advisory council meeting.  The SFY18 annual training for new members and ongoing training for all members will take place December 12, 2017.

APPENDIX 6.  AREA AGENCY ON AGING BOARD OF DIRECTORS

Composition of the Board of Directors

| Total Members Board Of Directors | Total Minority | Total with Disabilities | TOTAL Age 60+ | Board Members Who Are Age 60 Or Older |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | BLACK Age 60+ | HISPANIC Age 60+ | ASIAN Age 60+ | AMERICAN INDIAN Age 60+ | W/DISABILITIES Age 60+ | LOW INCOME Age 60+ | Participants Age 60+ |
| 37 | 6 | 2 |  | 2 | 1 | 0 | 0 | 2 | 0 | 2 |

| Name | Address/Phone Number | County Represented |
| --- | --- | --- |
| Randy McLemore | PO Box 1427 Anadarko, OK 73005 405.247.3105 (office) 405.933.0822 (cell) caddod2@sbcglobal.net | Caddo |
| Steve De Vaughan | PO Box 481 Binger, OK 73009 405.687.0883 (cell) sdevaughan@bop.gov | Caddo |
| Carlos Squires | RR 1, Box 101 Carnegie, OK 73015 405.643.5102 (office) 580.774.9500 (cell) | Caddo |
| Robert Crews* | PO Box 307 Apache, OK 73006 580.588.2075 (home) 580.695.4671 (cell) carolcrews@pldi.net | Caddo |
| Johnny Owens | 315 SW 5th Street Lawton, OK 73501 580.353.3717 (office) 580.678.0884 (cell) | Comanche |
| Dick Herrin* Secretary | PO Box 197 Fletcher, OK 73541 580.549.6550 (office) 580.591.1934 (cell) dh9743@att.net | Comanche |
| Jerry Pettijohn | 14322 NE 225th Fletcher, OK 73541 580.353.0532 (office) 580.695.3737 (home) | Comanche |
| Johnny Carroll | Cameron University 2800 West Gore Blvd Lawton, OK 73505 580.581.2335 (office) | Comanche |
| Edward Eschiti* Treasurer | 301 North Broadway Walters, OK 73572 580.875.3026 (office) 580.875.3852 (office) 580.512.7688 (cell) | Cotton |
| Ron Dinger | PO Box 144 Devol, OK 73531 580.299.3393 (home) arriva48@aol.com | Cotton |
| Weston Hoodenpyle | PO Box 179 Walters, OK 73572 580.875.2323 (office) 580.585.1881 (cell) | Cotton |
| Gerald Hayes | 622 Washington Street Walters, OK 73572 580.591.1135 (cell) 580.875.2074 (home) grhayes@netzero.com | Cotton |
| Mike Lennier * | 326 W Choctaw Chickasha, OK 73018 405.224.5211 (office) 405.224.2184 (office) gradydist2@yahoo.com | Grady |
| Christie Rainey | PO Box 146 Pocasset, OK 73079 405.459.6737 (home) 405.320.0032 (cell) | Grady |
| Gene Overton | PO Box 544 Minco, OK 73059 405.224.2172 (office) balermanok@sbcglobal.net | Grady |
| Michael Nealeigh | 1727 West Alabama Chickasha, OK 73018 405.574.1324 (office) mnealeigh@usao.edu | Grady |
| Billy Kidd | 220 N Main Waurika, OK 73573 580.228.2241 (office) 580.228.2303 (office) 580.467.8216 (cell) billykidd.jeffco1@gmail.com | Jefferson |
| Jim Bernard | 1406 North Meridian Waurika, OK 73573 580.228.2713 (office) 580.313.0041 (cell) loganbob17@sbcglobal.net | Jefferson |
| Royse Reagan* 2nd Vice President | 21616 E 2110 Road Terral, OK 73569 580.228.2760 (office) 580.437.2544 (home) reagoil@aol.com | Jefferson |
| J.C. Awtrey | PO Box 418 Ringling, OK 73456 580.662.2218 (home) | Jefferson |
| Charles Foster* 1st Vice President | PO Box 629 Purcell, OK 73080 405.527.3117 (office) 405.485.3388 (office) mcdist3@pldi.net | McClain |
| Marion “Bo” Cail | PO Box 263 Byars, OK 74831 405.783.4255 (office) 405.650.4469 (cell) boandmarla@gmail.com | McClain |
| Gaylon Gray | 1222 Cambridge Circle Purcell, OK 73080 405.527.3452 (office) 405.642.3513 (cell) gandjgray@hotmail.com | McClain |
| Ronnie Nelson | 100 East Center Road Goldsby, OK 73093 405.288.6675 (office) 405.570.8399 (cell) | McClain |
| Dee Bowen | PO Box 124 Comanche, OK 73529 580.255.4193 (office) 580.439.2206 (office) | Stephens |
| Sammy Richardson | 3703 Hwy 29 Marlow, OK 73055 580.467.8267 (cell) richardsonfarms@rocketmail.com | Stephens |
| Max Gallaway* | Rt 2, Box 157E Marlow, OK 73055 580.255.0510 (office) 580.255.5420 (home) maxgallaway@gmail.com | Stephens |
| Dale Davis | PO Box 1307 Chickasha, OK 73023 405.222.0550 (office) ddavis@chickashabank.com | Stephens |
| Jimmie Smith | 21532 County Road Tipton, OK 73570 580.335.2156 (office) 580.335.3421 (office) jcamps@pldi.net | Tillman |
| Eddie Whitworth | PO Box 399 Frederick, OK 73542 580.335.7551 (office) 580.335.2590 (office) | Tillman |
| Terry Wyatt* President | 23007 Crew 184 Hollister, OK 73551 580.335.3630 (office) 580.335.1907 (cell) wyatt@pldi.net | Tillman |
| Mary Hasenmyer | 1021 W 7th Grandfield, OK 73546 580.335.1384 (cell) m_hasenmyer@hotmail.com | Tillman |
| Fred Fitch Mayor of Lawton | 212 SW 4th 9th Street Lawton, OK 73501 580.581. 4792 (office) ffitch@cityoflawton.ok.us | Comanche |
| James Dorn Minority Rep | PO Box 211 Chickasha, OK 73023 405.224.0797 (home) 405.274.5263 (cell) | Caddo & Grady |
| Terri Parton Tribal Rep | WCD Tribal Group PO Box 729 Anadarko, OK 73005 405.247.8601 Terri.parton@wichitatribe.com | Caddo |
| Pedro S. Guevara | PO Box 121 Tipton, OK 73570 580.667.5424 (home) 580.471.5522 (cell) | Cotton, Jefferson & Tillman |
| Marcel Gigger* | 1206 S 3rd Duncan, OK 73533 580.252.3931 (home) 580.255.6954 (cell) | McClain & Stephens |
| Tribal Representative | PO Box 825 Anadarko, OK 73005 | Wichita, Caddo & Delaware Tribes |
| Tribal Representative | PO Box 885 Lawton, OK 73502 580.248.6300 (office) kcailuc@sbcglobal.net | Kiowa, Comanche & Apache Tribes |

* denotes member of executive committee

The role of the ASCOG Board of Director is to review and approve the Area Plan, Management Plan, RFP decisions and to guide the AAA director and staff in the administration and management of Title III programs.

APPENDIX 7.  AAA BOARD OF DIRECTORS SCHEDULE OF MEETING DATES

Full Board Meetings:

September 21, 2017

December 21, 2017

March 15, 2018

June 21, 2018

All meetings are scheduled to be held at 6:30 p.m. at the Red River Technology Center, Jerry D. Morris Business and Industry Service Center, 3300 W. Bois D’Arc, Duncan, OK  73533. The Red River Technology Center is ADA accessible.

APPENDIX 8. TRAINING SCHEDULE- AAA STAFF AND ANNUAL PROJECT TRAINING

New Hire Orientation and Annual Training

(See OAC Policy 340:105-10-44)

| New Hire Orientation/Annual Training for CY2016 |  |  |  |  |
| --- | --- | --- | --- | --- |
| AAA/Project | Staff Name | Date of Training | Training Topic | # Hrs |
| ASCOG AAA | Ken Jones Angela Halye Lillie Chaffin Cheris Brown Joanie Sutton Landra Colbert Harold Irby Laura Goldring Pete Goldring Mary Rogers Brenda Worley Tiffany Cochran Sue Boswell Cindy Hale Sammie Forrester Shirley Pattison Rachel Wooten Evelyn Shaw James Hammonds Leisha Saber Rebecca Briggs Karen Fulmer Bethany Sullivan Cathy Crockett Carla Davenport Dawn McCloud Brenda Clark | January 14 | Overview of OAA Title III Policy regarding intake forms and outreach Outreach Objectives Outreach Committee process and forms development Pilot Intake/Update forms Referral process AIM review | 5 |
| ASCOG AAA | Ken Jones Lewie Jeffries Rowena Scott Johnson Harold Mitchell Donna Fuava Pete Goldring Dede Baze Asia Clock | January 28 | Grant writing workshop for Title III grants | 3 |
| ASCOG AAA | Ken Jones Rachel Berry Kenny Berry Suzanne Aplin Lorene Miller Debra Smith Caroline Hines | February 4 | Grant writing workshop for Title III grants | 7 |
| Delta | Sheila Morris Bobbie McDonald | February 8 | Intake Form Training | 1.5 |
| ASCOG AAA | Ken Jones | March 3-4 | OARC Conference | 12 |
| ASCOG AAA | Ken Jones | March 8 | AAAAC Orientation | 1 |
| Delta | Ken Jones Sandy Leal April Houston | March 28 | AIM Training | 2 |
| ASCOG | Ken Jones | May10,12 | MAPS Training | 12 |
| ASCOG AAA | Ken Jones | April 12 | Governors Health Aging Summit | 6 |
| ASCOGAAA | Ken Jones Bethany Sullivan Caral Davenport Monica Day Dede Baze Rachel Berry Leisha Saber Sammie Forrester Kelli Copeland Erick Dennis Lorene Miller Cindy Hale Pete Goldring Tyler Johnson Nancy Bluml | June 23 | ASCOG.org website/training page Review OAA and related regs Review OK Title III Policy ASCOG Title III Policy All program reports All fiscal reports Assessment procedures Aging Service Network Job Specific Duties | 6 |
| No training in July |  |  |  |  |
| ASCOG AAA | Ken Jones | August 25 | Area Plan Training with DHS | 6 |
| MaddieLuke | Pete Goldring Sammie Forrester Carla Davenport Cindy Hale Kelli Copeland Laura Goldring | September 26 | October 2016 Training Module for Title III Staff | 30min |
| Maddie Luke | Pete Goldring Carla Davenport Sammie Forrester Cindy Hale | November 21 | November 2016 Training Module for Title III Staff | 30 min |
| Tipton | Amber Elliott | September 26 | October 2016 Training Module for Title III Staff | 30 min |
| Tipton | Amber Elliott | October 17 | November 2016 Training Module for Title III Staff | 30 min |
| ASCOG AAA | Ken Jones Kristina Brown | September 26 | October 2016 Training Module for Title III Staff | 2 |
| ASCOG AAA | Ken Jones Kristina Brown | October 17 | November 2016 Training Module for Title III Staff | 30 min |
| Delta Nutrition Project | April Houston Rebecca Briggs Landra Colbert Angela Halye Stacy Rodriguez Sharlet Hall Barbara Hanner Melissa Eddy Charlotte Davenport Norma Smith Kade McClure Jesse Macias Alberta White Duke Cagle Sandy Leal-Goodin Donna James Tristan Vinson Dennis Hoffman Cindy Yoder Linda Cross Susann Sales Lillie Chaffin Albert Thurman Diane Gonzales Evelyn Shaw Shashaine Rainville Pearl Taylor Deborah James Joe Harris Maria Luna Betty Thrash | October 12 October 12 October 17 October 17 October 17 November 21 | October 2016 Training Module for Title III Staff | 30 min 30 min 3 30 min 1 30 min 1 2 3 1.5 5 2.5 |
| Delta Nutrition Project | April Houston Landra Colbert Rebecca Briggs Angela Halye Barbara Hanner Evelyn Shaw Tristan Vinson Stacey Rodriguez Lillie Chaffin Sandy Leal-Goodin Sharlet Hall Charlotte Davenport Mary Rogers Glenda Fisher Duke Cagle Shashaina Rainville Alberta White Albert Thurman Jesse Macias Lisa Cross Cindy Hoder Dennis Hoffman Joseph R Harris Melissa Eddy David Tutt Norma Smith Donna James Maria Luna Diana Gonzales Betty Thrash | November 21 | November 2016 Training Module for Title III Staff | 30 min 1 1.5 4 |
| LAOK | Blanca Camacho Leona Denning Donna Ellsworth Norma Parsons Tyler C. Johnson Michael Wilson | October 12 | October 2016 Training Module for Title III Staff | 30 min 1 |
| LAOK | Donna Ellsworth Kade McClure Blanca Camacho Norma Parsons | November 30 | November 2016 Training Module for Title III Staff | 30 min |
| Cyril | Leisha Saber DiAnna Klenk Carolyn Myers | October 12 | October 2016 Training Module for Title III Staff | 30 min |
| Cyril | Leisha Saber DiAnna Klenk Carolin Myers | November 21 | November 2016 Training Module for Title III Staff | 30 min |
| Temple | Tiffany Cochran Janice Mason Deanna Romer | October 17 | October 2016 Training Module for Title III Staff | 30 min |
| Chickasha | Harold Irby | October 17 | October 2016 Training Module for Title III Staff | 4.5 |
| Elgin | Pam Pogue | October 17 | October 2016 Training Module for Title III Staff | 1 |
| Elgin | Pam Pogue | November 21 | November 2016 Training Module for Title III Staff | 30 min |
| Carnegie | Shirley Pattison Lona Schuermann | October 17 | October 2016 Training Module for Title III Staff | 1 |
| Center for Creative Living | Jeanine Lilly Monica Day Lorene Miller | October 17 | November 2016 Training Module for Title III Staff | 30 min |
| Anadarko | Karen Fulmer | November 21 | October 2016 Training Module for Title III Staff | 2.5 |
| Marlow | Cheris Brown | November 21 | October 2016 Training Module for Title III Staff | 30 min |
| Marlow | Cheris Brown | November 21 | November 2016 Training Module for Title III Staff | 1 |
| Duncan | Kris Brown Leisha Saber Ken Jones Dede Baze Angela Stevenson | December 28 | Review of Older Americans Act Review of NAPIS data purpose and area plan goals Review of AIM Manual | 3 |

*Required training topic

**List all trainings attended
APPENDIX 9. ADMINISTRATION FOR COMMUNITY LIVING (ACL)

STRATEGIC GOALS

All Americans-- including people with disabilities and older adults—should be able to live at home with the supports they need, participating in communities that value their contributions. To help meet these needs, the U.S. Department of Health and Human Services (HHS) created a new organization in 2012, the Administration for Community Living (ACL). This is ACL’s first strategic plan, encompassing many of the efforts and achievements of ACL’s two major components—the Administration on Aging and the Administration on Intellectual and Developmental Disabilities. ACL is charged with working with states, tribes, community providers, universities, nonprofit organizations, businesses and families to help older adults and people with disabilities live in their homes and fully participate in their communities. The ACL Strategic Plan established five goals that support their mission: Maximize the independence, well-being, and health of older adults, people with disabilities, and their families and caregivers.

ACL Strategic Goals 2013-2018  (ACL Strategic Plan is available online at www.acl.gov)

Goal 1: Advocacy

Advocate to ensure the interests of people with disabilities, older adults, and their families are reflected in the design and implementation of public policies and programs.

Goal 2: Protect Rights and Prevent Abuse

Protect and enhance the rights; and prevent the abuse, neglect, and exploitation of older adults and people with disabilities.

Goal 3: Individual Self-Determination & Control

Work with older adults and people with disabilities as they fully engage and participate in their communities, make informed decisions, and exercise self-determination and control about their independence, well-being, and health.

Goal 4: Long-Term Services and Supports

Enable people with disabilities and older adults to live in the community through the availability of and access to high-quality long-term services and supports, including supports for families and caregivers.

Goal 5: Effective and Responsive Management

Implement management and workforce practices that support the integrity and efficient operations of programs serving people with disabilities and older adults and ensure stewardship of taxpayers’ dollars.

APPENDIX 10. DESIGNATED FOCAL POINTS

| Focal Point Designation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Focal Point Name, Address, and Phone Number | Independent Senior Center | Title III Senior Center | CAP Agency | Other (church, library, courthouse, etc.) |
| Alex Community Center, PO Box 243, Alex, OK 73002, 405.785.9103 | X |  |  |  |
| Alfalfa Community Center, PO Box 148, Carnegie, OK 73015, 580.637.2276 | X |  |  |  |
| Amber Community/Senior Center, PO Box 3, Amber, OK 73004, 405.222.2175 | X |  |  |  |
| Binger Community Center, PO Box 184, Binger, OK 73010, 405.656.9255 | X |  |  |  |
| Blanchard Senior Citizens Center, PO Box 628, Blanchard, OK 73010, 405.485.9260 | X |  |  |  |
| Bradley Community Center, PO Box 87, Bradley, OK 73011, 405.462.7595 | X |  |  |  |
| Bray Senior Citizens Center, 1014 S. Brooks, Marlow, OK 73055, 580.658.2709 | X |  |  |  |
| Cache Community/Senior Citizens Center, PO Box 466, Cache, OK 73527, 580.429.3427 | X |  |  |  |
| Chattanooga Community Center, 1904 Washington, PO Box 183, Chattanooga, OK 73528, 580.597.3339 | X |  |  |  |
| Davidson Senior Citizens Center, PO Box 102, Davidson, OK 73530 No Phone | X |  |  |  |
| Dibble Senior Citizens, 12219 Firemans Road, Alex, OK 73002, 405.344.6789 | X |  |  |  |
| Douglass Community Center Organization, 707 King Place, Duncan, OK 73533, 580.255.3967 | X |  |  |  |
| Duncan Senior Citizens Center, Inc., 1110 N. 7th Street, Duncan, OK 73533, 580.255.6902 | X |  |  |  |
| Fort Cobb Senior Center, 312 Main Street, PO Box 281, Ft. Cobb, OK 73038, 405.643.2660 | X |  |  |  |
| Frederick Community Center, 100 Grand, Frederick, OK 73542, 580.335.7026 | X |  |  |  |
| Geronimo Nutrition Center, 101 Main Street, Geronimo, OK 73543, 580.353.3448 | X |  |  |  |
| Grandfield Multipurpose Senior Center, 123 W. First St., Grandfield, OK 73546, 580.479.3320 | X |  |  |  |
| Hastings Senior Citizens Center, PO Box 203, Hastings, OK 73548, 580.963.2531 | X |  |  |  |
| Hinton Senior Citizens Center, 515 W. Main St., PO Box 322, Hinton, OK 73047, 405.542.6454 | X |  |  |  |
| Indiahoma Senior Citizens Center, PO Box 38, Indiahoma, OK 73552, (580.246.3572 | X |  |  |  |
| Marlow Senior Citizens Center, 325 West Main St., Marlow, OK 73055, 580.658.5628 | X |  |  |  |
| Meers Senior Citizens Center, 12033 NW Rhoades Road, Lawton, OK 73507, 580.492.5128 | X |  |  |  |
| Minco Senior Citizens Center, PO Box 357, Minco, OK 73059, 405.352.5018 | X |  |  |  |
| Mt. Scott Community Bldg., 8819 NW 4 Mile Road, Lawton, OK 73507, 580.529.2619 | X |  |  |  |
| Newcastle Senior Citizens Center, PO Box 86, Newcastle, OK 73065, 405.387.2100 | X |  |  |  |
| Ninnekah Senior Citizens Center, PO Box 16, Ninnekah, OK 73067, 405.224.7434 | X |  |  |  |
| Patterson Center, #4 NE Arlington, Lawton, OK 73507, 580.581.3485 | X |  |  |  |
| Purcell Senior Citizens Center, 228 North 2nd Street, Purcell, OK 73080, 405.527.5070 | X |  |  |  |
| Rush Springs, Senior Nutrition Center, 400 W. Blakely #13, Rush Springs, OK 73082, 580.476.3168 | X |  |  |  |
| Ryan Senior Citizens Center, 400 Taylor #8, Rt 1 Box 8, Ryan, OK 73565, 580.757.2780 | X |  |  |  |
| Temple Senior Citizens Center, PO Box 95, Temple, OK 73568, 580.342.5017 | X |  |  |  |
| Tipton Area Senior Citizens Center, PO Box 554, Tipton, OK 73570, 580.667.4158 | X |  |  |  |
| Tuttle Senior Citizens Center, PO Box 134, Tuttle, OK 73089, 405.381.2606 | X |  |  |  |
| Velma Senior Citizens Center, PO Box 584, Velma, OK 73491, 580.444.3772 | X |  |  |  |
| Walters Senior Citizens Center, PO Box 465, Walters, OK 73572, 580.591.3212 | X |  |  |  |
| Wichita Mts. Area Senior Citizens Center, PO Box 331, Medicine Park, OK 73557, 580.529.3858 | X |  |  |  |
| Anadarko Nutrition Center, 417 W Main St., Anadarko, OK 73005, 405.247.4857 |  | X |  |  |
| Apache Tribe of Oklahoma Nutrition, 601 E Colorado, PO Box 1330, Anadarko, OK 73005, 405.247.6330 |  | X |  |  |
| Blanchard Nutrition Center, 101 S Main St., PO Box 1248, Blanchard, OK 73010, 405.485.9260 |  | X |  |  |
| Byars Nutrition Center, 207 E Ripley, Byars, OK 74831, 405.783.4468 |  | X |  |  |
| Cache Nutrition Center, 416 W C Ave., Cache, OK 73527, 580.429.3427 |  | X |  |  |
| Carnegie Nutrition Center, PO Box 1126, Carnegie, OK 73015, 405.654.1507 |  | X |  |  |
| Cement Nutrition Center, PO Box 351, Cement, OK 73017, 405.489.3803 |  | X |  |  |
| Chickasha Nutrition Center, PO Box 2101, Chickasha, OK 73012, 405.224.4315 |  | X |  |  |
| Comanche Nutrition Center, 410 S 2nd, Comanche, OK 73529, 580.439.5076 |  | X |  |  |
| Comanche County Nutrition Project, 920 SW Sheridan Rd, PO Box 2231, Lawton, OK 73502, 580.357.7764 |  | X |  |  |
| Cottonwood Center, PO Box 518, Verden, OK 73092, 405.453.7720 | X |  |  |  |
| Cyril Nutrition Center, PO Box 143, Cyril, OK 73029, 580.464.2300 |  | X |  |  |
| Delta Nutrition Program, 707 King Place, Duncan, OK 73533, 580.252.1174 |  | X |  |  |
| Duncan Northside Nutrition Center, 1110 N 7th St., Duncan, OK 73533, 580.252.1174 |  | X |  |  |
| Elgin Nutrition Center, 801 1st St., Elgin, OK 73538, 580.492.4980 |  | X |  |  |
| Frederick Nutrition Center, 102 East Grand, Grand Hotel, Frederick, OK 73542, 580.335.7026 |  | X |  |  |
| Geronimo Nutrition Center, 101 Main Street, Geronimo, OK 73543, 580.353.3448 |  | X |  |  |
| Hinton Nutrition Center, 501 W Main, Hinton, OK 73047, 405.542.6454 |  | X |  |  |
| Lawton North Nutrition Center, 1705 NW 20th St., Lawton, OK 73507, 580.581.3481 |  | X |  |  |
| Lawton Eastside Nutrition Center, Patterson Community Center, #4 Arlington, Lawton, OK 73501, 580.581.3485 |  | X |  |  |
| Lawton South Nutrition Center, 704 SW D Ave., Lawton, OK 73501, 580.355.5660 |  | X |  |  |
| Marlow Nutrition Center, 201 N Elm St., Marlow, OK 73055, 580.658.5773 |  | X |  |  |
| Pleasant Valley Nutrition Center, 1123 SW Monroe, Lawton, OK 73501, 580.581.3489 |  | X |  |  |
| Purcell Nutrition Center, 228 N 2nd, Purcell, OK 73080, 405.527.9462 |  | X |  |  |
| Randlett Nutrition Center, Randlett Community Bldg., Randlett, OK 73562, 580.281.3220 |  | X |  |  |
| Rush Springs Nutrition Center, 110 S 2nd St., Rush Springs, OK 73082, 580.476.3168 |  | X |  |  |
| Ryan Nutrition Center, 400 Taylor #8, Rt Box 8, Ryan, OK 73565, 580.757.2412 |  | X |  |  |
| Temple Nutrition Center, 201 S Commercial St., PO Box 652, Temple, OK 73568, 580.342.6944 |  | X |  |  |
| Walters Nutrition Center, 500 E California, PO Box 452, Walters, OK 73572, 580.875.2211 |  | X |  |  |
| Washington Nutrition Center, 219 N Turner, PO Box 624, Washington, OK 73093, 405.288.6404 |  | X |  |  |
| Wayne Nutrition Center, PO Box 271, Wayne, OK 73095, 405.449.3079 |  | X |  |  |
| Community Action Development, 105 S Main St., Frederick, OK 73542, 580.335.5588 |  |  | X |  |
| Community Action Development, 1401 Grant St., Apt., #1, Ryan, OK 73565, 580.757.2235 |  |  | X |  |
| Community Action Development, 102 E Texas St., Temple, OK 73568, 580.342.6967 |  |  | X |  |
| Delta Community Action, 223 W Washington St., Purcell, OK 73080, 405.527.6537 |  |  | X |  |
| Washita Valley Community Action, 205 W Chickasha, Ste. 5, Chickasha, OK 73018, 405.224.5831 |  |  | X |  |
| Ann Bradshaw, Sterling Housing Authority, 3 Hancock St., Sterling, OK 73567, 580.365.4862 |  |  |  | X |
| Nettie Fisher, Town Clerk, Town of Fletcher, PO Box 448, Fletcher, OK 73541, 580.549,6550 |  |  |  | X |
| Earl Yeahquo, 4 Cimarron Trail, Lawton, OK 73507, 580.355.0132 |  |  |  | X |

APPENDIX 11. AGING PROGRAM OUTPUT NARRATIVE

In SFY16, Maddie Luke provided chore services.  They will continue to focus on increasing services for  SFY17, though there was a delay in services at the beginning of the fiscal year due to budget delays.  In SFY16, MaddieLuke provided 261 units of chore to 20 participants, exceeding the ASCOG AAA goal of 1,000 units to 66 participants.  That goal has since been decreased due to reduced budgets. As state previously in this paragraph, There was a delay in services for SFY17 due to budget delays from the state.  As a result, numbers for SFY17 will be impacted and therefore the projected output was reduced to 150 units.  We anticipate recovery in SFY18, if we can avoid budget delays, and increased the goal to 200, still shy of SFY16 numbers because of anticipated budget reductions.   MaddieLuke will remain the SFY18 provider.

In SFY16, Home Delivered Meals exceeded the goal.  This was due in part on Delta’s improvement on food quality and food cost, increased outreach focus by MaddieLuke and Delta Nutrition as well as media campaigns and a reduction in goal to adjust to fewer sites served.   Delta provided 103,908 meals to 742 participants exceeding their goal of 94,000 units to 327 participants. Cyril provided 6,440 meals to 36 participants exceeding their goal of 5,695 meals to 20 participants. Temple provided 2,507 meals to 36 participants exceeding their goal of 2,032 meals to 8 participants. Overall ASCOG served 112,855 meals to 786 participants exceeding the goal of 74,000 meals to 650 participants.  SFY17 projections were reduced to 92,314 meals served to 1,174 participants due to mid-year site closures and the SFY18 goal was further reduced to 80,000 meals served to 1,000 participants due to having fewer sites in SFY18 than in SFY17 with no anticipated budget relief. We will extend contracts with Delta, Cyril and Temple for SFY18.  We are publishing an RFP for four sites in our southern area.

In SFY16, Congregate meals fell short of goal but within a ten percent margin.  Delta provided 181,800 meals to 1,459 participants missing their goal of 185,000 meals but exceeding their goal of 826 persons served. Cyril provided 4,921 meals to 48 participants exceeding their goal of 4,760 meals to 15 persons.  Temple provided 11,182 meals to 105 participants missing their goal of 12,713 units but exceeding their goal of 55 persons served. Overall ASCOG served 197,903 meals to 1,612 participants missing the goal of 220,000 meals for 1,700 persons served.  The congregate meals unit and persons served goal was reduced for SFY17 and SFY18 considering the SFY16 numbers and reduced budgets. SFY17 projections were reduced due to mid-year site closures and the SFY18 goal was further reduced to 137,502 meals for 1,326 participants, due to having fewer sites in SFY17 than in SFY16 with no anticipated budget relief. We will extend contracts with Delta, Cyril and Temple for SFY18.  We are publishing an RFP for four sites in our southern area.  We anticipate one fewer site in SFY18 and reduced the goal to 130,000 meals served to 1,250 participants.

In SFY16, Nutrition counseling fell far short of goal.  This is due to multiple factors, one was the transition of the service in SFY16 from ASCOG AAA to a subcontractor, Delta Nutrition. Another factor was a change in the definition of the unit restricting nutrition counseling to one unit per client per year.  In SFY17, this service is again provided directly by ASCOG AAA and already we are on track to exceed the numbers provided in SFY16.  The goal was also reduced to match the service definition and current expectations.In SFY16 ASCOG served 258 units of nutrition counseling to 24 participants. ASCOG has already implemented changes to our referral methods between contractors and has shown a increase in persons served in SFY17. The goal for SFY17 was since reduced to 60 units for 60 persons served. The goal for SFY18 was left the same as SFY17 as there is no expected increase in funding.  ASCOG will continue this as a direct service in SFY18 so that goal was kept at 60 and 60.

In SFY16, Transportation fell far short of goal. This was due to a change in insurance costs for Delta Nutrition which prohibited them from maintaining their own fleet and forcing them to depend on public service providers. Additionally, a mid-year funding reduction in state match was taken from transportation. Delta provided 12,889 trips to 68 participants missing their goal of 22,750 trips to 140 participants. Cyril provided 421 trips to 3 participants missing their goal of 1,038 trips to 5 participants. Temple provided 236 trips to 5 participants missing their goal of 1,967 trips to 14 participants. Overall ASCOG provided 14,358 trips to 211 participants, missing the goal of 31,000 trips but exceeding the goal of 140 persons served. In SFY17, ASCOG published two additional requests for proposals to establish a new provider to replace Delta and Cyril at their request.  ASCOG has retained Cyril for transportation. In SFY17 ASCOG awarded a contract with CADC for transportation to most of the ASCOG service area with the exception of the Cyril Nutrition Project which already had the contract. For SFY18, ASCOG is publishing an RFP for transportation to all current service areas except Cyril which will receive a contract extension.  As a result of changing providers, transportation units are expected to be lower for SFY17, 8,000 units for 40 passengers, but will hopefully rebound to 10,000 units for 50 passengers in SFY18.

In SFY16, Legal Assistance exceeded their goal.  This is due to a higher demand for the service.  Legal Aid provided 583 hours of legal assistance exceeding the goal of 436. Projections for SFY17 are higher for legal aid due to combining staff with other grant programs so their projection for SFY17 is now 800 hours. Their funding is not expected to change in SFY18 and their goal was left at 800 hours. ASCOG extended the Legal Aid contract for SFY17 and will extend the contract with Legal Aid for SFY18.

Nutrition Education. Missed their goal for SFY16 due to a change in the service definition limiting participation to participants who attend the nutrition site for the site manager presentation.  In SFY16, ASCOG provided 7,904 units of nutrition education to 1,699 participants missing the goal of 18,000 units but exceeding the goal of 1,500 persons served.  Since a change in interpretation of a unit served has been implemented, this goal was reduced for subsequent years. SFY17 numbers are projected to be lower due to site closures and should come in about 137,502 units provided to 1,326 participants.  That will further drop in SFY18 as there are few sites that will be open in SFY18 so the goal was set at 130,000 units for 1,250 participants. ASCOG will continue this as a direct service in both SFY17 and SFY18.

In SFY16, I&A did not reach its goal for SFY16, this is due in part to an increased goal for SFY16 and turnover in staff in this position.  ASCOG provided 277 units of I&A to 204 participants missing the goal of 300 units but exceeding the goal of 180 persons served. ASCOG project 270 units to 200 participants will be provided in SFY17 as there continues to be staff turnover in SFY17 due to reduced budgets.  We anticipate that goal to remain 270 units to 200 participants in SFY18. ASCOG continues to provide this as a direct service in SFY17 and will continue in SFY18 as well.

In SFY16, Outreach exceeded their goal for SFY16, this is due to increased need and name recognition for the outreach service provider.  MaddieLuke provided 766 units of outreach to 744 participants greatly exceeding the goal of 500 units to 500 participants. In SFY17, outreach is expected to achieve 699 units to 684 participants showing only a modest decline as budgets continue to tighten.  We do not anticipate funding reductions to this service in SFY18 so the goal is 700 units to 680 participants.  ASCOG extended the contract for MaddieLuke in SFY17 and will continue it again in SFY18.

In SFY16, Education and Training missed their goal, this is due to a decreased goal and improved capturing of service units.  The goal was reduced for SFY17 and 18 due to decreased units due to decreased funding and increased restrictions on the definition of E&T.  The Center for Creative Living provided 172 E&T classes in SFY16 missing the goal of 285 classes. ASCOG continues the contract with CCL for SFY17 and SFY18.  The goal for Education and Training was reduced in SFY17 and is projected to see 240 classes provided.  That is not expected to change in SFY18 so the goal was kept at 240.

In SFY16, Education/I&A goal was not met due to a vacancy in the position. That position has since been filled. ASCOG provided 28 units of Education I&A, missing our goal of 100, the goal having since been reduced due to the change in definition of education and training. ASCOG will continue this as a direct service in SFY17 and SFY18.  ASCOG projects 30 units of E&T for SFY17 and SFY18 so we kept that as the goal.  The goal was reduced from 100 due to reduced funding for the I&A position.

In SFY16, The Health Promotion Fell far short of goal in SFY16, this is due primarily to market penetration of the current service.  ASCOG has worked with service provider MaddieLuke to problem solve this and MaddieLuke is reaching out to other area partners to coordinate this service and increase participation.  MaddieLuke provided 88 units of health promotion to 20 participants greatly missing our goal of 640 units to 23 participants.  We reduced the goal for subsequent years to more appropriate targets.  MaddieLuke was contracted again in SFY17 for Health promotion and are on target to complete 80 units for 20 participants.  That goal was kept for SFY18 as no funding increases are expected.  We are retaining MaddieLuke as a contractor but are encouraging them to find help in providing additional units through partnerships.

Due to state budget reductions in SFY16, the home repair service was discontinued and no services were provided. Home repair will still not be a service in SFY17 and SFY18 as we do not expect to receive additional funds.

In SFY16, Coordination of Services goal was met. The goal was reduced for SFY17 and 18 due to a reduction in service providers from four to two.  ASCOG provided 5,946 hours of coordinator time exceeding our goal of 4,750 hours.  This was reduced for SFY17 due to the departure of two coordinators.  The aforementioned reduction for SFY17 changed the projection to 2,766 units.  That is also the goal for SFY18 as we do not anticipate further changes in budget for this service.  ASCOG will retain both Grandfield and Tipton for this service in SFY17 and SFY18.

In SFY16, Caregiver Information about services greatly exceeded their goal for both caregivers and GRRC.  However, access to services units have decreased and participation in support groups had greatly decreased.  Meanwhile, participation in respite services continues to rise and more funding is moved from access to services and support groups to provide the rising demand of respite services.  In SFY16, MaddieLuke provided 1,165 units of caregiver information greatly exceeding the goal of 225, 214 units of caregiver access missing the goal of 356, 68 units of support groups missing the goal of 389, and 5,760 units of respite missing the goal of 4,750.  MaddieLuke also provided 67 units of GRRC information exceeding their goal of 25, 35 units of GRRC missing their goal of 36 by one unit, 8 units of GRRC support groups missing the goal of 44, and 991 units of GRRC respite missing the goal of 507. MaddieLuke served 117 participants caregiver access missing the goal of 225 persons served, 17 participants caregiver support groups missing the goal of 36 persons served, and 72 participants caregiver respite missing the goal of 160 persons served.  MaddieLuke served 12 grandparents GRRC access missing the goal of 25 persons served, 7 grandparents in support groups exceeding the goal of 4 persons served, and 11 grandparents respite services missing the goal of 11 persons served. Based on current projects we anticipate SFY17 provider MaddieLuke to achieve the following units/UPS for each of the following services, CGI – 600, GPI – 33, CGA 180/160, GPA 25/23, CGG 85/25, GPG 6/5, CGR 4,500/60, GPR 600/12.  We will continue the contract with MaddieLuke in SFY18 and expect no change in funding so the goals for SFY18 will match the SFY17 projections.

APPENDIX 12. PROJECTED AGING PROGRAM OUTPUT (NEXT 3 YEARS)

(See note in Appendix 11.)

| Aging Program Output-Quantitative | SFY2016 NAPIS Report |  | SFY2017 Projected |  | SFY2018 Projected |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Service Categories | TOTAL UoS | TOTAL UPS | TOTAL UoS | TOTAL UPS | TOTAL UoS |  | TOTAL UPS |
| Personal Care | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Homemaker | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Chore | 261 | 20 | 150 | 10 | 200 | 15 |  |
| Home delivered meals | 116,319 | 823 | 92,315 | 1,174 | 80,000 | 1,000 |  |
| Adult day care/health | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Case Management | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Congregate Meals | 197,903 | 1,612 | 137,502 | 1,326 | 130,000 | 1,250 |  |
| Nutrition counseling | 26 | 24 | 60 | 60 | 60 | 60 |  |
| Assisted Transportation | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Transportation | 13,546 | 76 | 8,000 | 40 | 10,000 | 50 |  |
| Legal Assistance | 583 | XXXXXX | 800 | XXXXX | 800 | XXXXXX |  |
| Nutrition Education | 7,904 | 1,699 | 7,032 | 1,102 | 7,000 | 1,050 |  |
| Information & Assistance | 277 | 204 | 270 | 200 | 270 | 200 |  |
| Outreach | 766 | 744 | 699 | 684 | 700 | 680 |  |
| Advocacy/representation | XXX | XXXXXX | XXX | XXXXX | XXX | XXXXXX |  |
| Education/training | 1,004 | XXXXXXX | 240 | XXXXXX | 240 | XXXXXX |  |
| Education/information and assistance | 28 | XXXXXXX | 30 | XXXXXX | 30 | XXXXXXX |  |
| Health promotion Disease Prevention | 88 | 20 | 80 | 20 | 80 | 20 |  |
| Home repair | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Coordination of services | 5,946 | XXX | 2,766 | XXX | 2,766 | XXX |  |
| Information about services | 1,165 | XXX | 600 | XXX | 600 | XXX |  |
| Information about services/GRRC | 67 | XXX | 33 | XXX | 33 | XXX |  |
| Assistance with access to services | 214 | 117 | 180 | 160 | 180 | 160 |  |
| Assistance with access to services/GRRC | 35 | 12 | 25 | 23 | 25 | 23 |  |
| Counseling | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Counseling/GRRC | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Support groups | 68 | 17 | 85 | 25 | 85 | 25 |  |
| Support groups/GRRC | 8 | 7 | 6 | 5 | 6 | 5 |  |
| Training | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Training/GRRC | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Respite | 5,760 | 73 | 4,500 | 60 | 4,500 | 60 |  |
| Respite/GRRC | 991 | 11 | 600 | 12 | 600 | 12 |  |
| Supplemental Services | XXX | XXX | XXX | XXX | XXX | XXX |  |
| Supplemental Services/GRRC | XXX | XXX | XXX | XXX | XXX | XXX |  |

UoS – Units of Service; UPS – Unduplicated Persons Served

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: ____Caddo_____ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 29,405 |  |  |
| Total County pop. 60+ | 5,835 | 330 | 331* |
| Female 60+ | 3,185 | 200 | 201* |
| Male 60+ | 2,650 | 129 | 130* |
| African-American 60+ | 165 | 8 | 8 9 |
| American Indian 60+ | 1,020 | 12 | 14 13 |
| Asian 60+ | 10 | 2 | 2 2 |
| Hispanic/ Latino 60+ | 199 | 4 | 3 4 |
| Poverty (low income) 60+ | 835 | 103 | 105* |
| Poverty (low income) minority 60+ | 349 | 14 | 14 |
| Limited English proficiency 60+ | 29 | 0 | 0 1 |
| Individuals residing in rural isolated 60+ | 7,282 | 300 | 280* |
| GGRC 60+ | 105 | 1 | 2 |
| Individuals living alone 60+ | 1,485 | 161 | 161 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 1,590 | 13 | 15 |
| *Individuals with disabilities 60+ (self- identified) | 2,460 | 55 | 58 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 83 | 90 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **875 | **52 | 55 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: ____Comanche_____ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 123,100 |  |  |
| Total County pop. 60+ | 16,955 | 658 | 660 |
| Female 60+ | 9,385 | 415 | 416 |
| Male 60+ | 7,570 | 243 | 244 |
| African-American 60+ | 2,275 | 120 | 122* |
| American Indian 60+ | 990 | 19 | 21 |
| Asian 60+ | 625 | 5 | 6 |
| Hispanic/ Latino 60+ | 645 | 23 | 25 |
| Poverty (low income) 60+ | 1,340 | 198 | 200* |
| Poverty (low income) minority 60+ | 499 | 70 | 75 |
| Limited English proficiency 60+ | 370 | 1 | 1 |
| Individuals residing in rural isolated 60+ | 2,119 | 143 | 145 |
| GGRC 60+ | 430 | 3 | 3 |
| Individuals living alone 60+ | 4,750 | 275 | 280 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 5,505 | 18 | 20 |
| *Individuals with disabilities 60+ (self- identified) | 7,050 | 91 | 95 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 151 | 155 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **2,543 | **116 | 120 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: __Cotton_______ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 6,170 |  |  |
| Total County pop. 60+ | 1,335 | 123 | 125 |
| Female 60+ | 745 | 71 | 70 |
| Male 60+ | 590 | 52 | 53 |
| African-American 60+ | 39 | 2 | 3 |
| American Indian 60+ | 94 | 9 | 10 |
| Asian 60+ | 8 | 0 | 0 |
| Hispanic/ Latino 60+ | 54 | 3 | 4 |
| Poverty (low income) 60+ | 115 | 61 | 50 |
| Poverty (low income) minority 60+ | 88 | 8 | 11 |
| Limited English proficiency 60+ | 15 | 0 | 0 |
| Individuals residing in rural isolated 60+ | 1,748 | 114 | 115 |
| GGRC 60+ | 20 | 0 | 0 |
| Individuals living alone 60+ | 305 | 62 | 64 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 314 | 0 | 5 |
| *Individuals with disabilities 60+ (self- identified) | 470 | 9 | 14 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 14 | 18 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **926 | **19 | 21 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: ___Grady______ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 52,450 |  |  |
| Total County pop. 60+ | 9,900 | 286 | 289* |
| Female 60+ | 5,195 | 184 | 197* |
| Male 60+ | 4,705 | 102 | 103 |
| African-American 60+ | 210 | 4 | 5 |
| American Indian 60+ | 325 | 8 | 8 |
| Asian 60+ | 22 | 0 | 1 |
| Hispanic/ Latino 60+ | 145 | 4 | 4 |
| Poverty (low income) 60+ | 945 | 83 | 94* |
| Poverty (low income) minority 60+ | 71 | 7 | 7 |
| Limited English proficiency 60+ | 50 | 0 | 0 |
| Individuals residing in rural isolated 60+ | 2,341 | 244 | 246 |
| GGRC 60+ | 255 | 1 | 1 |
| Individuals living alone 60+ | 2,345 | 121 | 121 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 2,580 | 6 | 8 |
| *Individuals with disabilities 60+ (self- identified) | 3,840 | 53 | 55 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 76 | 80 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **1,485 | **304 | 310 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: _Jefferson________ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 6,445 |  |  |
| Total County pop. 60+ | 1,560 | 160 | 162 |
| Female 60+ | 810 | 97 | 100 |
| Male 60+ | 750 | 63 | 65 |
| African-American 60+ | 4 | 0 | 1 |
| American Indian 60+ | 119 | 11 | 12 |
| Asian 60+ | 0 | 0 | 0 |
| Hispanic/ Latino 60+ | 68 | 4 | 7 |
| Poverty (low income) 60+ | 195 | 75 | 77 |
| Poverty (low income) minority 60+ | 22 | 8 | 10 |
| Limited English proficiency 60+ | 20 | 0 | 0 |
| Individuals residing in rural isolated 60+ | 435 | 153 | 155 |
| GGRC 60+ | 15 | 0 | 0 |
| Individuals living alone 60+ | 400 | 79 | 81* |
| Estimated Totals |  |  |  |
| Veterans 60+ | 315 | 8 | 10 |
| *Individuals with disabilities 60+ (self- identified) | 565 | 40 | 42 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 53 | 55 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **234 | **30 | 32 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: _McClain________ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 34,470 |  |  |
| Total County pop. 60+ | 6,420 | 357 | 360 |
| Female 60+ | 3,485 | 217 | 218 |
| Male 60+ | 2,935 | 140 | 142 |
| African-American 60+ | 45 | 3 | 4 |
| American Indian 60+ | 205 | 9 | 10 |
| Asian 60+ | 0 | 0 | 0 |
| Hispanic/ Latino 60+ | 75 | 6 | 6 |
| Poverty (low income) 60+ | 545 | 89 | 90 |
| Poverty (low income) minority 60+ | 16 | 5 | 6 |
| Limited English proficiency 60+ | 0 | 0 | 0 |
| Individuals residing in rural isolated 60+ | 802 | 102 | 105 |
| GGRC 60+ | 145 | 0 | 0 |
| Individuals living alone 60+ | 1,400 | 153 | 155 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 1,575 | 11 | 15 |
| *Individuals with disabilities 60+ (self- identified) | 2,600 | 43 | 45 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 59 | 62 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **963 | **56 | 60 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: __Stephens_______ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 44,850 |  |  |
| Total County pop. 60+ | 10,085 | 602 | 605 |
| Female 60+ | 5,510 | 363 | 364 |
| Male 60+ | 4,575 | 239 | 241 |
| African-American 60+ | 170 | 33 | 34 |
| American Indian 60+ | 249 | 21 | 22 |
| Asian 60+ | 50 | 0 | 0 |
| Hispanic/ Latino 60+ | 180 | 3 | 4 |
| Poverty (low income) 60+ | 890 | 191 | 193 |
| Poverty (low income) minority 60+ | 62 | 28 | 29 |
| Limited English proficiency 60+ | 85 | 0 | 0 |
| Individuals residing in rural isolated 60+ | 12,894 | 539 | 550 |
| GGRC 60+ | 155 | 2 | 2 |
| Individuals living alone 60+ | 2,360 | 263 | * 270 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 2,655 | 18 | 20 |
| *Individuals with disabilities 60+ (self- identified) | 4,030 | 97 | 100 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 156 | 160 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **1,512 | **108 | 110 |

* Per OKN506 report

** Per 15% of senior population/population served.

APPENDIX 13.  DEMOGRAPHICS OF OLDER PERSONS IN THE PSA

| Type of population by county: ___Tillman______ | # County (from AGiD per instructions) | Estimated Population Served in SFY 2014 2016 | Estimated Population To Be Served in SFY 2018 |
| --- | --- | --- | --- |
| Total County pop. | 7,980 |  |  |
| Total County pop. 60+ | 1,895 | 139 | 140 |
| Female 60+ | 1,070 | 83 | 84 |
| Male 60+ | 825 | 56 | 56 |
| African-American 60+ | 130 | 4 | 5 |
| American Indian 60+ | 18 | 3 | 4 5 |
| Asian 60+ | 0 | 0 | 0 |
| Hispanic/ Latino 60+ | 205 | 14 | 15 |
| Poverty (low income) 60+ | 225 | 38 | 39 |
| Poverty (low income) minority 60+ | 129 | 10 | 12 |
| Limited English proficiency 60+ | 69 | 2 | 2 3 |
| Individuals residing in rural isolated 60+ | 536 | 127 | 130 |
| GGRC 60+ | 30 | 0 | 0 |
| Individuals living alone 60+ | 565 | 67 | 69 |
| Estimated Totals |  |  |  |
| Veterans 60+ | 469 | 1 | 2 |
| *Individuals with disabilities 60+ (self- identified) | 805 | 20 | 22 |
| *Individuals at risk for institutional placement 60+(3 or more ADLS) | No Data Found | 32 | 33 |
| *Individuals with Alzheimer’s Disease and related disorders 60+ (self- identified) | **284 | **25 | 26 |

* Per OKN506 report

** Per 15% of senior population/population served.

| APPENDIX 14. LIST OF NON-TITLE III SERVICES IN PSA |  |  |  |
| --- | --- | --- | --- |
| SERVICE | *Listing of Services | Counties Available | Gaps in Services |
| In-Home Services | Advantage Waiver | All eight |  |
| Accessible Medical Care | Duncan Regional Hospital, Comanche County Memorial, Lawton Indian Hospital, Frederick Hospital, Jefferson County Hospital, Purcell Municipal Hospital, Grady Memorial Hospital, Ft. Cobb Health Clinic | Caddo, Comanche, Grady, Jefferson, McClain, Stephens and Tillman | Cotton County – residents go to Lawton, Duncan or Wichita Falls. |
| Adult Day Care/ Respite Care | Goodwill Adult Day Care, Nora O’Neal Adult Day Care Center, Chateau de South, Chi Day Care Center | Caddo, Comanche, Grady and Stephens | Cotton, Jefferson, McClain and Tillman |
| Adult Protective Services | DHS APS | All eight | N/A |
| Title VI , Part A Nutritional and Supportive Services and Title VI, Part C Native American Caregiver Support Services | Chickasaw Nation Nutrition in Duncan and Purcell with caregiver programs for tribal members, Comanche Nation Nutrition and caregiver services | All eight | N/A |
| Case Management Services | ASCOG Managed Care coordinates with many home health agencies | All eight | N/A |
| Transportation Services for the Elderly and Disabled | Lawton Area Transportation Service, Red River Transportation, Washita Valley Transportation, Delta Public Transit, Kiowa Nation Public Transportation and Comanche Nation Public Transportation | All eight | Transportation for medical care in all eight counties. |
| Meals on Wheels or Mobile Meals Programs | Mobile Meals Inc. in Lawton, independent senior centers in all eight counties, Meals on Wheels in Chickasha | All eight | N/A |
| Independent Senior Centers | Refer to focal points. | All eight | N/A |
| Senior Volunteer Programs | RSVP and Foster Grandparents | Comanche, McClain | Caddo, Cotton, Grady, Jefferson, Stephens and Tillman |
| Disability Services | Transportation services (listed above), housing authorities, Duncan Group Homes, Goodwill | Stephens, Comanche | Caddo, Cotton, Grady, Jefferson, McClain and Tillman |
| Mental Health Services | OLDR Program, Silver Linings, Reflections, Red Rock Mental Health Center, Christians Family Counseling, Taliaferro, McClain County Treatment Center and New Horizons | Comanche, Stephens, Grady, McClain | Caddo, Cotton, Jefferson and Tillman |
| LTC Planning/Option | ASCOG Managed Care, Promises Eldercare Planning | All eight | N/A |
| **Other | ASCOG Masonic Charity Foundation Grant, Calvary Baptist Dental Clinic, Salvation Army, Catholic Charities, Homeless shelters in Lawton and Duncan, Christians Concerned, Marlow Samaritans, Comanche Helping Hands | All eight | N/A |

*Can include private pay, OKDHS services, non-profit, Medicare, Medicaid, volunteer programs, etc.

**List any additional services available in PSA

APPENDIX 15.  CURRENT POVERTY GUIDELINES

#### U.S. FEDERAL POVERTY GUIDELINES USED TO DETERMINE FINANCIAL ELIGIBILITY FOR CERTAIN FEDERAL PROGRAMS

There are two slightly different versions of the federal poverty measure: poverty thresholds and poverty guidelines.

The poverty thresholds are the original version of the federal poverty measure.  They are updated each year by the Census Bureau.  The thresholds are used mainly for statistical purposes — for instance, preparing estimates of the number of Americans in poverty each year.  (In other words, all official poverty population figures are calculated using the poverty thresholds, not the guidelines.) Poverty thresholds since 1973 (and for selected earlier years) and weighted average poverty thresholds since 1959 are available on the Census Bureau’s Web site.  For an example of how the Census Bureau applies the thresholds to a family’s income to determine its poverty status, see “How the Census Bureau Measures Poverty” on the Census Bureau’s web site.

The poverty guidelines are the other version of the federal poverty measure. They are issued each year in the Federal Register by the Department of Health and Human Services (HHS).  The guidelines are a simplification of the poverty thresholds for use for administrative purposes — for instance, determining financial eligibility for certain federal programs.

The poverty guidelines are sometimes loosely referred to as the “federal poverty level” (FPL), but that phrase is ambiguous and should be avoided, especially in situations (e.g., legislative or administrative) where precision is important.

Key differences between poverty thresholds and poverty guidelines are outlined in a table under Frequently Asked Questions (FAQs). See also the discussion of this topic on the Institute for Research on Poverty’s web site.

The January 2017 poverty guidelines are calculated by taking the 2015 Census Bureau’s poverty thresholds and adjusting them for price changes between 2015 and 2016 using the Consumer Price Index (CPI-U).   The poverty thresholds used by the Census Bureau for statistical purposes are complex and are not composed of standardized increments between family sizes.  Since many program officials prefer to use guidelines with uniform increments across family sizes, the poverty guidelines include rounding and standardizing adjustments in the formula.

### HHS POVERTY GUIDELINES FOR 2017

The 2017 poverty guidelines will be in effect as of January 31, 2017.
See also the Federal Register notice of the 2017 poverty guidelines, published January 31, 2017

| 2017 POVERTY GUIDELINES FOR THE 48 CONTIGUOUS STATES AND THE DISTRICT OF COLUMBIA |  |
| --- | --- |
| PERSONS IN FAMILY/HOUSEHOLD | POVERTY GUIDELINE |
| For families/households with more than 8 persons, add $4,180 for each additional person. |  |
| 1 | $12,060 |
| 2 | $16,240 |
| 3 | $20,420 |
| 4 | $24,600 |
| 5 | $28,780 |
| 6 | $32,960 |
| 7 | $37,140 |
| 8 | $41,320 |

APPENDIX 16. MANAGEMENT PLAN NARRATIVE

Based on the feedback received from surveys and from public forums, ASCOG selected the following goals to address in the coming year.

*Outcome one: To increase utilization of home-based services by seven percent over the next four years.

~Goal one:  Long-term services and supports:  Enable people with disabilities and older adults to live in the community through the availability of and access to high-quality long-term services and supports, including supports for families and caregivers.

*Outcome two:  Reduce instances of fraud and disallowed spending to less than one-half of one percent.

~Goal two:  Effective and Responsive Management:  Implement management and workforce practices that support the integrity and efficient operations of programs serving people with disabilities and older adults and ensure stewardship of taxpayers’ dollars.

*Outcome three:  Increase community knowledge of available services by increasing number of community partnerships by twenty percent.

~Goal three:  Advocacy:  Advocate to ensure the interests of people with disabilities, older adults, and their families are reflected in the design and implementation of public policies.

In  SFY16, ASCOG  hosted eight public hearings and forums to provide education to and receive input from the public regarding expected changes to long-term care services and supports through the incoming coordination of care service model.  Input was varied.  Because of the concerns raised about nutrition site funding most comments from the sites addressed concern for future funding.

In order to achieve the second goal,  In SFY16 ASCOG adopted a code of ethics policy for all Title III employees.  The ethics policy and procedures is expected to protect seniors and prohibit activities that could potentially damage the integrity of our programs.  The code of ethics was distributed to all ten subcontractors for Title III services for input prior to the final adoption of the code of ethics.  The code of ethics was published on the ASCOG website.

For the third goal, ASCOG facilitated a policy conference through coordination with community partners and established new MOUs with community partners.  For SFY17, ASCOG will provide support to and assist in facilitating the advocacy activities of the Oklahoma Silver Haired Legislature.

In SFY16ASCOG supported the OSHL session for SFY16 by providing the ASCOG I&A to serve as an OSHL liaison and providing the AAA director to serve as parliamentarian.  The I&A served one day of the OSHL session while the Director served two days.  ASCOG also provided staff support for minutes for the local OSHL four quarterly meetings.

. ASCOG’s Ombudsman Supervisor Ruben Sotelo served as the Lawton Senior Summit liaison until his death.  He was replaced by Dacia Nix. Ruben attended six meetings.

APPENDIX 17. INDIRECT COST RATE PROPOSAL

APPENDIX 18. PUBLIC HEARING SUMMARY AND CHANGES, IF ANY, MADE TO AP

Complete and submit with Area Plan application. Be specific and provide details needed to understand reasons for changes made, if any.

1.	Location of Public Hearing	Attendance	Date

- Ringling 	12	10/03/2016

- Ryan	20	10/03/2016

- Frederick	21	10/06/2016

- Lawton North	12	11/15/2016

- Duncan	20	12/01/2016

- Walters	15	12/20/2016

- Chickasha	63	01/12/2017

- Anadarko	23	02/07/2017

2.	Summarization of comments from Public Hearings.

Ringling: No comments.

Ryan: No comments except to say they want to keep their senior center open and the nutrition project is important to them.

Frederick: No comments, only questions about possible budget reductions.

Lawton North: Comments were related solely to food preferences which were referred to Delta Nutrition for consideration.

Duncan Public Hearing:

- December 13, 2016

- Red River Technology Center

- Kristina Brown Notes

- 9:00

- Ken Jones, ASCOG called the Public Hearing to order at 9:00 am

- Ken explained the purpose of the public hearing and encouraged the present members to comment and ask questions at any point as their feedback is extremely i8mportant to update and change our Area plan.

- The fiscal year was explained, as well as the cuts affecting the nutrition programs including but not limited to sourcing out of meals, no referrals from advantage, dietician mandates, and several other decisions made by lawmakers that have had dramatic effects on the programs.

- ASCOG budget cuts for AAA, including the elimination and combination of positions as well as the assumption of new responsibilities by current employees.

- State budgeting shortfalls, specifically DHS 43 million dollar shortfall, which is hoped to be fixed by a legislative intervention.

- Ken opened the floor for Public comment, questions, concerns.

- Haljean Gillespie “Is there a solution?”

- Petra Taylor “Why are people in nursing homes and assisted living centers getting care from the facility and outside sources like home health care or hospice? That’s double dipping.”

- Charles Watson “My son receives federal grants to help him get training to find a job.”

- Ken Jones, SCSEP explanation

- Rubye Benson “There are programs for utility assistance, like round up”

- Kristina Brown, Explanation of current utility programs and Charities willing to assist programs.

- Ken Jones, Masonic will reopen utility assistance to aid the need for seniors with utilities.

- Ken Jones, Thank you, and Break until AAA Advisory Meeting

Walters: No comments

Chickasha: No comments

Anadarko:  Thankful for nutrition program.

4.	Comments received, but no changes made to the Area Plan as a result of the 	Public Hearings because:

None.

Due to budget restrictions and staff reductions, additional Title III services are not possible, however the Masonic grant was extended to help those in need of utility assistance.

APPENDIX 19. ADVISORY COUNCIL SUMMARY AND CHANGES, IF ANY, MADE TO AP

1.	Date	Attendance

a.  December 13, 2017_                         _20________

2.	Summarization of Comments from the Council meeting.

No comments received.

3.	Changes made in the Area Plan as a result of the Council's Suggestions.

None

APPENDIX 20.  AAA BOARD OF DIRECTORS SUMMARY AND CHANGES, IF ANY, MADE TO AREA PLAN

1.	Date    	Attendance

a. _February 16, 2017_____	__15_______

2.	Summarization of comments from the Board meeting.

Agreed to change volunteer travel to 25 cents per mile to help cover Ombudsman volunteers. Approved as submitted and modified.

3.	Changes made in the Area Plan as a result of the Board's suggestions.

Changed volunteer mileage to 25 cents per mile.  $1,000 was moved from AAA Advisory Council travel to ombudsman volunteer travel.